Short-Video Business Model
Risk Register

Foundation gaps, business risks, safeguards, fallbacks, and a 90-day action plan

Created: 26 September 2026, 5:05 PM EDT
Last modified: 26 September 2026, 5:05 PM EDT

The decision in one sentence Treat Shorts as the cost of building an audience—not as the main product—and do not remove BalRam’s review gate until the automated fact, content, safety, and moderation checks are proven.

Working review — not yet incorporated into the pipeline plans

# How to use this document

This document combines two reviews: the foundational-gap review and the wider business-model review. It does not change the existing project files. It turns the findings into one plain-language plan for deciding what must be fixed before the pilot, before full automation, and before scale.

| Read first | What it answers |
| --- | --- |
| Executive decision | What the project should assume now |
| 18 missing foundations | What is absent from the current plans |
| Full risk register | What can go wrong and the fallback |
| Storage and reuse | How to preserve assets for long-form |
| Economics | How the project can realistically pay |
| 30/60/90-day plan | What to do in what order |

Evidence boundary The risk logic and measured VM facts come from the two completed reviews. Dollar amounts, platform limits, policy dates, vendor prices, and revenue rates are working estimates or review inputs. Recheck them at the time of purchase, account setup, or API build. Tax notes are planning prompts, not tax advice.

# Executive decision: build for trust and recovery first

The present plan is not ready for fully automatic publishing. Its strongest safety control is still BalRam’s own review. If that review disappears before replacement checks are proven, factual mistakes, weak visuals, private-data leaks, unsafe topics, and comment problems can go public without a reliable stop.

| Decision | Plain-language rule | Why |
| --- | --- | --- |
| Revenue | Plan year one at $0 ad revenue | Shorts ads may not cover even modest costs. |
| Pilot | Use 90 days to prove trust and traction | Views alone do not prove a durable business. |
| Automation | Keep review until four checks are proven | Facts, content, guardrails, and moderation need automated gates. |
| Storage | Use the VM as a desk, not a warehouse | One machine must not hold the only copy. |
| Continuity | Scripts run mechanics; people handle judgment | The system should survive reduced agent access. |

## Five items can break the pilot immediately

| Order | Must exist | Minimum proof |
| --- | --- | --- |
| 1 | Fact verification | Unsourced claim cannot publish. |
| 2 | Content-quality QC | Bad or mismatched visual is quarantined. |
| 3 | Private-data protection | Capture profile is clean and frames are scanned. |
| 4 | Code backup + rebuild | Fresh machine rebuild succeeds. |
| 5 | Review overflow rule | Backlog pauses output without silent failure. |

# Part I — The 18 missing foundations

These are not extra features. They are controls that support the promises already made in the plans. “Before pilot” items come first; “before full automation” items must be proven before the review gate is removed; “before scale” items protect the business as volume grows.

## Before pilot

| ID | Gap / what breaks | Primary fix | Fallback |
| --- | --- | --- | --- |
| F1 | No fact-check before publishing — A script can publish a wrong launch, feature, or price. | Every claim needs a source stored with the video; re-check it before publishing. | Quarantine the video for manual review; publish an evergreen item instead. |
| F2 | No content-quality check — Technical checks can pass a misleading, garbled, offensive, or mismatched visual. | Add spelling, visual-match, unsafe-image, and logo checks. | Hold the video; replace the suspect scene and re-run checks. |
| F3 | Screen captures can expose private data — An email, bookmark, account name, or personal page could be burned into a public video. | Use a clean browser profile and scan frames for personal information. | Block screen-capture publishing; use a clean recreated demo. |
| F4 | No code version history or rebuild guide — A VM problem could erase five codebases and weeks of work. | Put every codebase in private version control and write a rebuild guide. | Keep an encrypted second copy and test a full rebuild. |
| F5 | Review queue has no time limit or overflow rule — If reviews pause, videos pile up or get rushed through. | Set a review deadline, backlog limit, and automatic generation hold. | Skip publishing slots safely; resume from the oldest approved video. |

## Before full automation

| ID | Gap / what breaks | Primary fix | Fallback |
| --- | --- | --- | --- |
| F6 | Costs are watched but not stopped — A retry loop or heavy batch can burn the month’s allowance. | Set hard per-video and monthly caps; pause at the limit. | Step down from 3 to 2 to 1 video per day. |
| F7 | Media is not backed up away from the VM — Loss of source assets breaks reposts, compilations, and winner reuse. | Back up masters, covers, metadata, and reusable raw files off the VM. | Keep a second independent copy and run restore drills. |
| F8 | Account recovery is not defined — A lockout or stolen session can stop publishing or lose the channel. | Use strong two-step security, recovery methods, and backup managers. | Keep a recovery kit and continue on the other platforms. |
| F9 | Topic sources and queue protection are unclear — The system can run out of good ideas or publish old news as new. | Name each source, check it several times daily, and alert below a two-day queue. | Switch to the evergreen backlog until sources recover. |
| F10 | Safety rules are not measured — Rules may block too much, block too little, or make BalRam the permanent safety filter. | Define the checking method and measure missed issues and false alarms. | Return uncertain topics to manual review and lower output. |
| F11 | No numeric format stop rules — A weak format can burn weeks because “good enough” is undefined. | Set minimum retention, view, and sample-size rules before the pilot. | Pause the format and test one controlled alternative. |
| F12 | No comment-moderation policy — Scams, abuse, and inconsistent replies can damage trust. | Create reply tone, spam, hiding, and escalation rules. | Turn on stricter native controls and hold comments for review. |
| F14 | Hook testing has no workable method — Parallel versions can waste upload quota and produce unclear results. | Test hooks sequentially with a minimum sample and one decision rule. | Pause automated tests and compare hooks manually in pilot reviews. |

## Before first affiliate link

| ID | Gap / what breaks | Primary fix | Fallback |
| --- | --- | --- | --- |
| F13 | Affiliate disclosure is not specified — A link can go live without a clear disclosure. | Lock disclosure wording and placement for every platform. | Block affiliate publishing until the disclosure check passes. |

## Before first long-form video

| ID | Gap / what breaks | Primary fix | Fallback |
| --- | --- | --- | --- |
| F15 | Long-form assembly is incomplete — Vertical clips may become cropped or ugly in a wide video. | Define format, reframing, bridge script, voiceover, and QC. | Build the long-form video manually from approved masters. |

## Before scale

| ID | Gap / what breaks | Primary fix | Fallback |
| --- | --- | --- | --- |
| F16 | Disaster recovery lacks targets and steps — A backup is not useful if nobody knows how fast or how far back it restores. | Set recovery-time and recovery-point targets; document and test restoration. | Use the second copy and a manual publishing week while systems rebuild. |
| F17 | No channel-loss contingency — A termination or demonetization can erase audience and income. | Prepare appeal steps and start an owned audience path. | Continue on other platforms and seed a replacement channel. |
| F18 | Playlist automation has no build task — The plan calls it automatic, but nothing is assigned to build it. | Add a build task and a test gate. | Mark playlists manual or optional until built. |

## Ten unclear statements that need a real specification

These phrases sound complete, but a builder cannot implement or test them yet.

| ID | Unclear point | Decision needed |
| --- | --- | --- |
| V1 | YouTube upload cost is written as an approximate, conflicting figure. | Verify the live quota cost before building the uploader. |
| V2 | Pilot gates refer to niche baselines that were never recorded. | Record the baseline values before pilot results can influence them. |
| V3 | Playlists are called automatic without an implementation task. | Add the task or label the feature manual. |
| V4 | Daily review is estimated at 15–20 minutes without evidence. | Measure week one and set the real service target. |
| V5 | Monthly review promises 100% accuracy checking at 90+ videos. | Define the automated re-check method and human sample. |
| V6 | Affiliate attribution can be “inferred,” but inference is undefined. | Write the exact rule; otherwise call it unknown. |
| V7 | The location of scheduled-publishing authorization is garbled. | Rewrite it clearly in one named record. |
| V8 | Usage is compared with an allowance that has no number. | Set monthly and per-video limits. |
| V9 | Title A/B variants are logged, but there is no test design. | Set sample size, time window, and winner rule. |
| V10 | Visual continuity refers to a snapshot ID without a full mechanism. | Explain the workflow or remove the promise. |

## Useful later, but not launch foundations

| Item | Why it can wait |
| --- | --- |
| Title/thumbnail A/B system | Needs enough traffic to create a useful baseline. |
| Multiple languages | Expand only after English channel proves itself. |
| Full email marketing system | Start audience capture simply; build automation later. |
| Competitor dashboard | A weekly manual scan is enough in the pilot. |
| Advanced attribution | Meaningful only after revenue exists. |
| Community features | Already optional; do not distract from pilot reliability. |

# Part II — The business must work without ad revenue

Base-case financial rule Budget the pilot and the first year as if Shorts advertising pays nothing. Affiliate income is the first realistic revenue line; sponsors come after proof of audience; weekly long-form is the higher-value viewing format.

## Working economics — estimates, not a locked budget

| Measure | Working estimate | How to use it |
| --- | --- | --- |
| Short cash cost | $0.45–$1.70 each | Planning range; midpoint about $1. |
| Monthly cash burn | $50–$170 | About 90 Shorts + four long-form videos. |
| Founder review time | 15–30 hours/month | Measure in week one; do not hide it. |
| Shorts ad break-even | About 2M views/month | Illustrates why ads are not the base case. |
| Affiliate break-even | About five $20 commissions | Roughly covers a $100 month. |
| Storage by month 12 | About 0.18 TB | Based on 12–15 GB monthly intake. |

## Revenue ladder

| Order | Revenue path | Plain-language role |
| --- | --- | --- |
| 1 | Affiliate links | Can earn from the first useful video; diversify programs. |
| 2 | Sponsors | Higher value, but only after the audience is proven. |
| 3 | Weekly long-form | Far better revenue per view than Shorts in the review estimate. |
| 4 | Shorts ad share | Treat as upside, not the plan. |
| 5 | TikTok / Instagram payouts | Use mainly as distribution unless real data proves otherwise. |

# Part III — Full risk register

Every risk has two responses. The primary action reduces the chance or impact. The fallback keeps the project operating after the first action is not enough.

## Business, revenue, and marketing

| ID / level | Risk and consequence | Primary action | Backup |
| --- | --- | --- | --- |
| B1 Critical | Advertising does not cover costs — Shorts ad income may stay tiny even with strong views. | Budget year one at $0 ad revenue; build affiliate income first. | Reduce cadence and let long-form plus sponsors carry the project. |
| B2 Critical | Cold start lasts longer than expected — A new channel may get only small view counts for months. | Use 90-day pass, pivot, or pause gates based on real retention and growth. | Make fewer, stronger videos and use searchable long-form. |
| B3 High | TikTok format earns little or nothing — The planned short length may not qualify for meaningful creator rewards. | Treat TikTok as a funnel; test a longer platform-specific version. | Stop optimizing for TikTok payout and focus on affiliate clicks. |
| B4 High | Human review becomes the hidden largest cost — Three daily reviews can consume 15–30 hours each month. | Batch reviews and improve automated checks so rejections are rare. | Drop to two videos daily or assign a trained reviewer. |
| B5 High | The news treadmill forces bad choices — News goes stale quickly; rushing increases factual mistakes. | Mix news with evergreen explainers so no weak story is forced out. | Switch to evergreen videos and a weekly news roundup. |
| B6 High | The format has no lasting advantage — Competitors can copy an AI-made format very quickly. | Compete on trusted research, clear explanations, speed, and a consistent voice. | Own a narrower lane, such as AI pricing and cost changes. |
| B7 High | Sponsors arrive later than hoped — A new channel may have no sponsor income for months. | Start affiliate-first and approach sponsors only after proof of audience. | Build a small paid guide or toolkit later. |
| B8 Medium | Sponsor contracts create cash and control risk — Slow payment, cancellation, and exclusivity can block better work. | Use deposits, short payment terms, a kill fee, and limited exclusivity. | Walk away, blacklist non-payers, and cap any sponsor’s share of revenue. |
| B9 Medium | Affiliate programs change their terms — Commissions, cookies, or whole programs can disappear. | Use at least three unrelated programs and prefer recurring commissions. | Change links quickly through one central registry. |
| B10 Medium | The AI-news niche cools — Audience fatigue can reduce demand for the whole channel. | Keep the two backup niches warm and maintain evergreen stock. | Launch the best backup only after a clear four-week decline trigger. |
| B11 Medium | Copycats or impersonators confuse viewers — A faceless brand is easy to imitate and attach to scam links. | Use a consistent voice and visual system; actively report impersonation. | Pursue trademark protection after revenue justifies it. |
| B12 High | The chosen content style may not fit the market — AI illustrations plus voiceover may lose to human or hybrid formats. | Use pilot retention and click data to kill weak formats quickly. | Test a hybrid format; if the niche fails, use a backup niche. |
| B13 Medium | Platform payouts or thresholds change — Revenue formulas can change after the audience is built. | Keep platform payouts below 30% of planned revenue. | Use platforms only for distribution; monetize elsewhere. |
| B14 Medium | Currency conversion quietly raises cost — USD tools and CAD finances create spreads and swings. | Track costs in CAD with a buffer and keep a USD balance when sensible. | Price sponsors in USD and convert less often. |
| B15 Medium | Tax arrives as a surprise — Withholding and income-tax obligations can erase apparent profit. | Complete required payer forms and reserve part of income from day one. | Use a Canadian accountant before the first meaningful revenue month. |
| B16 Medium | Founder time is not counted — The project can look profitable while consuming valuable evenings. | Track review, sales, and firefighting hours as a real cost. | Delegate or cut cadence when the time budget is exceeded. |
| B17 High | A wrong news claim damages trust — One incorrect price or feature can hurt audience and sponsor confidence. | Block unsourced claims and store sources with each script. | Correct publicly within 24 hours and replace the bad asset. |

## Platforms, policy, and AI suppliers

| ID / level | Risk and consequence | Primary action | Backup |
| --- | --- | --- | --- |
| P1 Critical | YouTube may class the channel as inauthentic — High-volume, repeated AI templates can be denied monetization or removed. | Give every video an original angle and measure template similarity. | Cut to one commentary-led video daily and appeal with process records. |
| P2 High | Synthetic-media labels become stricter — A missing or wrong label can limit or remove a video. | Disclose synthetic media by default and store the flag with the asset. | Change one shared setting across uploaders and pause uncertain posts. |
| P3 High | Feeds quietly reduce AI-content reach — Everything can appear healthy while distribution collapses. | Track reach against a rolling baseline and strengthen original research. | Move effort to the platform and format still distributing. |
| P4 Medium | YouTube API quota or approval changes — Uploads can stop even though finished videos exist. | Use efficient calls, monitor quota, and request more before it is needed. | Upload finished files manually while the API route is repaired. |
| P5 Medium | Automation rules change — A previously allowed posting method can become non-compliant. | Use official APIs and review terms on a schedule. | Return to native manual posting without losing finished content. |
| P6 Medium | TikTok or Instagram tightens automated posting — These platforms may restrict access or posting patterns. | Use official access, normal human-paced scheduling, and approved account types. | Post manually or deprioritize the affected platform. |
| P7 High | Music or voice rights are challenged — A likeness or music complaint can remove a video or create legal cost. | Use original or commercially licensed media and save proof for every asset. | Remove the claim, swap the disputed stem, and re-render. |
| P8 Medium | Affiliate-disclosure rules change — Both platforms and regulators can act on unclear promotion. | Make disclosure a required publishing field. | Change the shared template and re-check live sponsored posts. |
| P9 Medium | News sources or feeds fail — The topic queue can dry up while the schedule keeps demanding videos. | Keep several sources and at least seven days of evergreen ideas. | Switch fully to evergreen content and flag the outage. |
| P10 Critical | The business depends too much on YouTube — One company controls audience, discovery, policy, and a large income path. | Post on three platforms and start an owned audience path in the pilot. | Continue elsewhere and use the archive to seed a replacement channel. |
| P11 High | Agent or free-tier capacity shrinks — Less agent time or lower tool limits can starve the pipeline. | Make scripts and scheduled jobs run the mechanics; budget paid capacity. | Use the written manual runbook and reduce cadence. |
| P12 High | Voice or image models disappear or change — A sudden voice or visual shift breaks brand consistency. | Pre-approve two substitute voices and two image models; pin versions. | Use a stored voice backlog and frame the switch as a new season. |

## Technology, security, and operations

| ID / level | Risk and consequence | Primary action | Backup |
| --- | --- | --- | --- |
| T1 Critical | Everything is on one machine — One failure can remove code, assets, records, and recovery instructions. | Nightly off-machine media backup plus remote private code repositories. | Weekly encrypted second copy and quarterly restore test. |
| T2 Critical | Publishing partly fails without being noticed — One or two platforms may miss a post while the system reports success. | Use a per-video, per-platform ledger and verify each post is live. | Alert on stuck items and reconcile the ledger weekly. |
| T3 High | Tokens expire or access is revoked — Posting stops suddenly and can look like a content problem. | Check token health daily and keep a tested rotation guide. | Use manual posting while access is renewed. |
| T4 Critical | AI quota runs out mid-month — Voice or image production stops before the month ends. | Measure demand, buy headroom, and forecast month-end use daily. | Switch vendors or step down from 3 to 2 to 1 video daily. |
| T5 High | Tool prices rise or exchange rates move — The cost per video can double without a clear stopping rule. | Track cost per video in CAD and enforce a monthly ceiling. | Use pre-tested substitutes or pause Shorts. |
| T6 High | The VM disk fills — Renders can corrupt and scheduled jobs can fail together. | Keep only hot work locally; alert at 70% and 85% use. | Abort renders below 10 GB free and offload oldest raw files. |
| T7 Medium | Rendering becomes a bottleneck — Two CPU cores may not keep up with retries and long-form assembly. | Use a queue, low concurrency, work outside the small temporary disk, and measure times. | Burst to paid rendering or a small dedicated server. |
| T8 Medium | YouTube is mistaken for an archive — Downloaded copies are compressed, uploads use quota, and a strike can erase them. | Store originals in object storage with checksums. | Recover the best available copy, mark it degraded, and rebuild from raw assets. |
| T9 Critical | Credentials or personal data leak — Secrets in logs or personal details in a capture can become public. | Keep secrets in the vault, scrub logs, scan commits, and use a clean capture profile. | Revoke and rotate access immediately; follow an incident checklist. |
| T10 High | High-volume posting triggers abuse systems — Repeated automated posts can cause restrictions or strikes. | Stay within limits and keep each video meaningfully different. | Pause automation, appeal, and post manually. |
| T11 High | Monitoring fails with the same machine — If the watcher shares the VM, it disappears during the outage. | Use an external heartbeat and separate error tracking. | Use a second watcher and a simple daily status check. |
| T12 Medium | Software or API versions quietly expire — A small dependency change can stop a whole platform. | Pin versions, watch end-of-life dates, and run weekly private smoke tests. | Use a separate adapter per platform and the manual-upload path. |
| T13 Critical | A compromised VM publishes harmful content — Upload access can be used to post scams through the trusted channel. | Use least-privilege access and keep the review gate as a security control. | Use a kill switch to revoke tokens; backup manager removes the app. |
| T14 Medium | Comment volume overwhelms people and systems — Growth can turn replies, scams, and abuse into daily operational load. | Use native filters now and one daily comment queue. | Add automated triage or a trained moderator at scale. |
| T15 Low now | Analytics outgrows the simple database — Large output can make full-history pulls and reports slow. | Use incremental data pulls and archived raw responses. | Move to a managed database only when measurements show strain. |
| T16 Critical | No plain recovery guide exists for BalRam — If Muse is unavailable, accounts and manual posting steps may be unclear. | Create a simple recovery guide with account roles, locations, and five manual steps. | Keep a secure offline copy and publish masters manually for a week. |

# Part IV — Storage that supports future long-form videos

The project should keep one high-quality vertical master for each Short, plus the pieces needed to rebuild it. Wide-screen versions and platform copies are temporary outputs, not masters.

## Recommended three-layer storage

| Layer | What lives there | Rule |
| --- | --- | --- |
| Hot workspace | Current-week edits and active renders | Fast working area only; not the only copy. |
| Primary archive | Masters, subtitles, voice stems, metadata, reusable raw assets | Versioned object storage with checksums. |
| Independent copy | Second provider or BalRam-controlled local drive | Must survive loss of the primary archive. |

## Keep, archive, or delete

| Asset class | Examples | Retention |
| --- | --- | --- |
| Master | Final 1080×1920 video, subtitles, voice stem, metadata | Keep long term in two places. |
| Raw ingredient | Images, screen captures, script, edit instructions | Keep 12 months; longer if reuse score is high. |
| Derivative | 16:9 render, platform copy, temporary thumbnail | Delete after verified publishing; rebuild when needed. |

## Each video needs a reusable record

| Field | Purpose |
| --- | --- |
| Topic and controlled tags | Find related material without browsing folders. |
| Hook text and script | Reuse the idea or create a bridge. |
| Checksums and storage keys | Prove the file and locate it. |
| Platform IDs | Connect the master to published copies. |
| Reuse score, 1–5 | Let the long-form compiler choose proven material. |
| Rights and disclosure status | Prevent reuse without the required permission or label. |

Long-form rule The compiler searches the catalog for high-reuse clips, fetches masters, creates a wide-screen version, adds bridge narration, and sends the finished video through review. Missing masters cause a loud failure—never a silent substitute.

## Storage options from the review — verify prices before purchase

| Option | Suggested role | Review estimate / caution |
| --- | --- | --- |
| Backblaze B2 | Primary archive | Low-cost object storage; about $1.25/month at the month-12 estimate. |
| Cloudflare R2 | Public ingestion files | Useful when an API needs a public URL; roughly $2.70/month at month 12. |
| Hetzner Storage Box | Independent second copy | Flat-cost remote copy; not a public content-delivery layer. |
| BalRam local drive | Third copy | Physical control, but not enough as the only offsite backup. |
| YouTube private/unlisted | Do not use as archive | Re-encoded copies, quota use, and platform-loss risk. |
| Git LFS | Do not use for video archive | Better for code pointers than large media history. |

## Muse-side storage: what is known and what is not

| Status | Finding | Meaning |
| --- | --- | --- |
| Measured | About 100 GB total disk and 98 GB free at review time | The 90-day estimate can fit today. |
| Measured | 2 CPU cores, 7 GB memory, 512 MB temporary memory disk | Rendering and temporary-file placement need care. |
| Estimated | 12–15 GB new media each month | The local disk can become tight around month 6–8. |
| Not documented | No confirmed storage quota, file cap, or persistence guarantee | Do not interpret “not documented” as unlimited. |
| Operating rule | Log disk growth weekly; alert at 70% and 85% | Move old raw assets before the system is under pressure. |

# Part V — Scale breaks people and quotas before storage cost

| Scale | First things to break | Required response |
| --- | --- | --- |
| Pilot: 3/day | Review backlog, silent publishing, quota surprises | Use ledgers, limits, and human review. |
| 10× output | Human review, upload quotas, two-core rendering | Request quota early, add render capacity, redesign review. |
| 10× audience | Comments, spam, analytics attention | Add moderation and focused reporting. |
| 100× output | All quotas, databases, account design, staffing | Treat as a different business; require a new architecture review. |
| 100× audience | Moderation becomes a staffing choice | Budget people and stronger community systems. |

## Systems that free tiers or Muse alone should not carry

| Need | Practical answer | When |
| --- | --- | --- |
| Media archive | Paid object storage + second copy | Week 1 |
| Public media URL | Object storage with controlled public access | Before API ingestion |
| External monitoring | Heartbeat service outside the VM | Before pilot |
| Error history | Separate error tracking and archived logs | Before pilot |
| Large rendering | On-demand render service or dedicated server | Only when queue proves the need |
| Large analytics | Managed database or archive-query setup | Only when SQLite measurably strains |
| Secrets and recovery | Secure Vault, limited permissions, backup managers | Before connecting accounts |

## What works if Muse is limited or unavailable

| Work | Target state | Human role |
| --- | --- | --- |
| Mechanical pipeline | Scripts handle drafting, rendering, checks, scheduling, posting, ledgers, and backup | Supervise exceptions. |
| Judgment | Fact truth, quality, news value, and difficult policy calls remain gated | BalRam or a trained reviewer decides. |
| Continuity mode | Finished masters can be posted manually from the archive | Follow the one-page runbook. |
| Capacity control | Automatic 3→2→1 daily step-down protects quota and money | Approve sustained changes. |
| Recovery | Code and media restore from independent copies | Use tested steps, not memory. |

Minimum-survivable configuration Version-controlled scripts, scheduled mechanical jobs, BalRam’s review gate, automatic quota step-down, manual-upload instructions, two independent backups, a recovery guide, and funded voice/image capacity.

# Part VI — A simple playbook for platform and vendor changes

| Stage | What the system does | Escalation |
| --- | --- | --- |
| Detect | Watch policy pages, API changes, vendor notices, error spikes, and reach changes. | Any limited, removed, or newly labelled video starts a review. |
| Assess | Within 48 hours, identify the affected step, likely revenue effect, and severity. | A business-killer reaches BalRam the same day. |
| Adapt | Use the prepared setting change, substitute vendor, or manual process. | Log the change so the next occurrence is a lookup, not a crisis. |
| Confirm | Run a private or limited test and verify the result. | Do not restore full cadence until the check passes. |

## Prepared responses

| Change | First response | Fallback |
| --- | --- | --- |
| Disclosure rule | Change the shared upload setting. | Pause uncertain videos. |
| API ends | Switch to the named adapter or new version. | Post manually for one cycle. |
| Monetization tightens | Raise originality and cut repetitive cadence. | Operate on affiliate and sponsor income. |
| Feed reach falls | Shift effort to the working format and platform. | Use evergreen search-led long-form. |
| Vendor price rises | Benchmark the substitute. | Step down cadence. |
| Model disappears | Use pre-approved voice or image model. | Use stored backlog while rebuilding style. |

# Part VII — 30/60/90-day action plan

This order prevents a polished-looking pilot from running on fragile foundations. Each item should have an owner, a due date, and visible proof.

## Days 0–30: make failure safe

| Priority | Action | Proof of completion |
| --- | --- | --- |
| 1 | Build fact, content, privacy, and disclosure gates. | A deliberately bad test video is blocked. |
| 2 | Back up code and media off the VM. | A clean restore rebuilds one video. |
| 3 | Secure platform accounts and define recovery. | Backup manager and recovery methods confirmed. |
| 4 | Add publish ledger, token checks, and outside monitoring. | A simulated partial failure creates an alert. |
| 5 | Set cost, quota, disk, and review-backlog limits. | Each limit safely pauses or steps down output. |
| 6 | Write the one-page manual publishing and outage guide. | BalRam can follow it without the builder. |

## Days 31–60: prove the operating model

| Priority | Action | Proof of completion |
| --- | --- | --- |
| 1 | Measure real review time, costs, storage growth, and render time. | Weekly report uses measured values. |
| 2 | Run the pilot with mixed news and evergreen content. | Queue stays above the minimum without weak filler. |
| 3 | Set numeric pass, pivot, and stop rules. | Decisions use locked thresholds and sample sizes. |
| 4 | Test sequential hooks without duplicate-upload waste. | Winner rule is repeatable. |
| 5 | Build comment moderation and correction workflows. | Spam and one seeded error follow the playbook. |
| 6 | Pre-approve backup voice and image models. | Same test scripts render acceptably on substitutes. |

## Days 61–90: prove the business before scale

| Priority | Action | Proof of completion |
| --- | --- | --- |
| 1 | Judge content-market fit with the preset gates. | Pass, pivot, or pause decision is documented. |
| 2 | Test affiliate economics without assuming ad income. | Clicks, conversions, and net value are measured. |
| 3 | Publish and review the first long-form compilation. | Wide format, bridges, rights, and QC all pass. |
| 4 | Run a quarterly-style restore and account-recovery drill. | Recovery time and data loss meet the targets. |
| 5 | Decide whether the review gate can change. | Only proven automated controls replace human checks. |
| 6 | Approve or reject any move beyond pilot scale. | New capacity and staffing plan exists before expansion. |

# Part VIII — Decisions still needed

| Decision | Why it matters | Do not assume |
| --- | --- | --- |
| Storage-account owner | Controls billing, recovery, and legal ownership. | Whether it is BalRam or a project identity. |
| Developer approvals | YouTube, TikTok, and Meta access can lead the schedule. | That approval will be immediate. |
| Voice-crisp vendor/model | Determines backup, licensing, and portability. | Whether it is a custom clone or stock voice. |
| Review SLA and backlog limit | Sets the true pilot workload and missed-slot behavior. | That 15–20 minutes/day is accurate. |
| Cost ceiling | Controls cadence and vendor choices. | That “minimum cost” is measurable without a number. |
| Recovery targets | Define acceptable downtime and data loss. | That any backup is automatically good enough. |
| Owned-audience method | Reduces dependence on one platform. | That cross-posting alone creates portability. |
| Account and tax structure | Affects contracts, payments, and records. | Any legal or tax treatment without professional confirmation. |

## Assumptions made for this document

| Assumption | Meaning |
| --- | --- |
| Current operating target | Three Shorts per day plus one weekly long-form video. |
| Revenue base case | Advertising contributes $0 in year one. |
| Human review | BalRam remains the publishing gate during the pilot. |
| Media format | 1080×1920 vertical master is the reusable source. |
| Current machine | The measured VM snapshot is temporary capacity, not a guarantee. |
| Currency and prices | Review figures are approximate and must be refreshed before commitment. |

# Final recommendation

Proceed with the pilot only after the five pilot-breakers are closed and demonstrated. Keep the human review gate through the 90-day proof period. Do not scale output because views look exciting; scale only after the project proves factual trust, reliable delivery, recoverability, and a revenue path that works without Shorts advertising.

The test that matters If YouTube disappeared, the VM failed, Muse access shrank, and one AI vendor changed terms in the same week, the project should still retain its code, master files, account recovery path, and a way to publish manually. Build to pass that test.

## Review basis and limitations

This register consolidates the foundational-gap review and the full business-model review completed on 26 September 2026. The foundational review checked the project’s plans, specifications, policies, ledgers, task lists, and schemas; one suspected metrics-schema gap was removed after the schema was found. The wider review covered business, economics, marketing, platform policy, AI suppliers, storage, security, continuity, and scale.

No existing pipeline plan or task file was changed by these reviews. Before any purchase, tax decision, account change, platform build, or budget lock, verify the current official rules, account eligibility, quotas, prices, terms, and ownership requirements.