SHORT-VIDEO
COMPREHENSIVE BUSINESS PLAN

AI Technology Education · Multi-platform · Review-first

A complete map of the business, the build, the controls, the choices,
and the fallback routes — written for practical review.

Created: 26 September 2026, 8:28 PM EDT
Last modified: 26 September 2026, 8:39 PM EDT
Planning horizon: pilot through repeatable scale

# How to use this plan

Read the first six pages to make decisions. Use the remaining sections as the operating blueprint and reference manual.

| If you want to… | Go to… |
| --- | --- |
| Understand the whole strategy | Executive summary |
| Decide what happens now | Decision dashboard |
| Approve the rollout | Three-phase roadmap |
| See what depends on what | Dependency map |
| Challenge assumptions | Scenario and stop-loss section |
| Inspect one business area | Relevant operating section |
| See every major failure route | Risk and contingency register |
| Check public rules | Sources and evidence notes |

Status boundary This is the proposed master plan. It does not authorize account creation, spending, publishing, or removal of the human review gate. Those actions remain separate decisions.

## Contents

Automatic contents — update this field in Word if page numbers are not shown.

# Executive summary

The opportunity is not “make many AI Shorts.” The opportunity is to build a trusted, low-cost education brand whose short videos create discovery, whose deeper material creates trust, and whose recommendations, sponsors, and future products create revenue.

Recommended decision Proceed as a controlled 90-day pilot. Keep human approval. Treat advertising revenue as zero in the base case. Prove audience value, reliable operations, and one non-ad revenue path before scaling.

## The business in one page

| Question | Working answer |
| --- | --- |
| Customer | Busy, non-technical people who want useful AI updates without hype. |
| Problem | AI changes quickly; most coverage is noisy, technical, promotional, or late. |
| Promise | Clear, verified explanation: what changed, why it matters, and what to do. |
| Channel one | AI Technology Education. |
| Content engine | News-reactive explainers + evergreen teaching + recurring series. |
| Distribution | YouTube Shorts, Instagram Reels, Facebook Reels, TikTok; long-form on YouTube. |
| Revenue order | Affiliate proof → sponsors → long-form → owned products; ads are upside. |
| Moat | Trusted judgment, source records, fast corrections, useful archives, learning system. |
| Operating model | Five independent pipelines sharing one controlled learning record. |
| Safety | No sensitive, objectionable, child-focused, political, or controversial material. |
| Launch rule | No public publishing until factual, visual, rights, privacy, and technical gates pass. |
| Scale rule | Scale only a format with repeatable retention, manageable cost, and revenue evidence. |

## What makes it durable

| Point | Meaning / action |
| --- | --- |
| Self-sustaining | income is diversified; each content line has a cost ceiling; founder time is counted. |
| Self-improving | every video creates structured learning, but changes require enough evidence and controlled tests. |
| Self-healing | known failures have bounded retries, substitute providers, quarantine, alerts, and manual mode. |
| Self-extensible | new platforms, niches, languages, and products plug into defined interfaces instead of changing the whole system. |
| Recoverable | code, media, credentials, ledgers, and operating instructions survive the loss of one machine or one person. |
| Hard to copy | the advantage is the evidence system, editorial judgment, audience trust, and reusable knowledge—not the template. |

## Decision dashboard

| Recommendation | Phase | Owner decision |
| --- | --- | --- |
| Keep one niche and one channel first | 1 | Confirm channel name |
| Keep the crisp female US narrator | 1 | Already chosen |
| Keep review on every pilot video | 1 | Already chosen |
| Use 1–2 strong Shorts/day at first | 1 | Choose pace before launch |
| Start an evergreen reserve before news | 1 | Approve 14-video reserve |
| Add one weekly long-form pilot | 2 | Approve after 20 Shorts |
| Open affiliate links only after trust checks | 2 | Approve programs and disclosures |
| Approach sponsors after audience proof | 2 | Approve rate card and outreach |
| Build email capture after a useful offer exists | 2 | Approve lead magnet and provider |
| Add languages or second niche | 3 | Park until English economics work |
| Use paid promotion | 2/3 | Only on proven organic winners |
| Remove “3 per day” as a fixed promise | Now | Replace with capacity-based range |

## What to keep now, park, remove, or decide

| Bucket | Items |
| --- | --- |
| KEEP NOW | One niche; review gate; original media; source ledger; five pipelines; backups; incident controls; simple scorecard; evergreen buffer. |
| PARK | Languages; second niche; memberships; merchandise; courses; advanced attribution; large database; paid render farm; staff moderation. |
| REMOVE | Guaranteed daily volume; ad-revenue break-even claims; “fully automatic” as a near-term goal; tools chosen only because free; copying one edit across platforms. |
| DECIDE | Brand name; pilot pace; monthly cash cap; cumulative stop-loss; affiliate categories; email timing; business structure; outside accountant/lawyer triggers. |

## Non-negotiable launch gates

| Gate | Proof required | If missing |
| --- | --- | --- |
| Claims | Each factual claim has a current source and review record. | Do not publish. |
| Visuals | Every visual matches the sentence; no private data or unsafe imagery. | Replace scene. |
| Rights | Commercial use and reuse rights recorded for voice, image, music, fonts, and capture. | Use approved substitute. |
| Disclosure | AI and commercial-relationship fields set for each platform. | Hold post. |
| Technical | File passes platform profile; scheduled post is verified live. | Use manual route. |
| Recovery | Code and media restore has been tested from another location. | Pilot remains limited. |
| Capacity | Review queue, tool quota, storage, and budget have headroom. | Reduce cadence. |

# 1. Strategy: build a trusted media asset, not a content factory

Automation lowers production cost. It does not create customer value. The strategy must make every video useful, recognizably original, and connected to a durable business asset.

## The strategic choices

| Choice | Recommended position | Reason |
| --- | --- | --- |
| Audience | Non-technical professionals and curious consumers | Large enough to grow; specific enough to serve. |
| Job to be done | Understand an AI change and decide whether to care or act | Creates a repeatable editorial promise. |
| Editorial stance | Practical, calm, evidence-first, no hype | Separates the brand from generic AI news. |
| Publishing pace | Capacity based, not quota based | Quality and trust are bottlenecks. |
| Format mix | Short discovery + long-form depth + owned recap | Each format performs a different job. |
| Business model | Media plus recommendations, partnerships, and later products | Avoids dependence on one payout source. |
| Primary moat | Decision quality and accumulated knowledge | Templates and AI tools are easy to copy. |
| Growth rule | One proven channel before a portfolio | Prevents multiplying an unproven system. |

## The promise to the viewer

Every item should answer four questions in plain words: What changed? Why does it matter? Who is it for? What should the viewer do next? If a topic cannot answer those questions without exaggeration, it is not ready.

The channel should not pretend that a synthetic narrator is a human expert. Authority comes from verifiable sourcing, useful explanations, visible corrections, and consistency—not from an invented personality.

## The moat ladder

| Step | Action |
| --- | --- |
| 1 | Reliable publishing. This is necessary, but competitors can copy it. |
| 2 | Consistent voice and visual grammar. Recognizable, but still copyable. |
| 3 | A tested editorial method. Harder to copy because it includes judgment and quality history. |
| 4 | A structured knowledge base of claims, sources, outcomes, and audience questions. This compounds. |
| 5 | Audience trust, direct audience access, partner relationships, and reusable intellectual property. These are the durable assets. |

Stop-loss principle The project is allowed to fail cheaply. It is not allowed to drift expensively. A pre-set cash limit, time limit, and decision date protect the owner from sunk-cost thinking.

# 2. Audience, market, and competition

The market should be understood from viewer problems upward, not from a giant “creator economy” headline number downward.

## Audience segments to test

| Segment | Need | Winning proof |
| --- | --- | --- |
| AI-curious beginner | Know what a tool does without jargon | Saves, shares, profile visits |
| Busy professional | Decide whether a feature matters at work | Long-form clicks, newsletter interest |
| Small-business operator | Save time or money with practical tools | Qualified affiliate clicks |
| Student / career switcher | Understand concepts and build confidence | Repeat viewing, series completion |
| Existing AI user | Track pricing, features, and comparisons | Comments with specific follow-up questions |

## Research before scaling

| Purpose | Build now |
| --- | --- |
| Find the highest-value audience problem. | Interview or survey 10–20 target viewers; collect their wording; test five problem-led series. |

| Proof | Trigger | Fallback |
| --- | --- | --- |
| One segment repeatedly watches, saves, returns, and asks useful next questions. | No segment separates after 30–50 posts. | Narrow the promise or test the backup niche without adding another live channel. |

## Competitive intelligence loop

| Point | Meaning / action |
| --- | --- |
| Map substitutes, not only channels | newsletters, podcasts, blogs, tool directories, vendor channels, search results, and AI assistants all compete for the same answer. |
| Track patterns, not vanity numbers | topic choice, promise, opening, evidence style, series design, comments, offer, posting rhythm, and update practice. |
| Study weak spots | outdated advice, unmarked sponsorship, jargon, missing comparisons, no correction process, and repeated templates are openings. |
| Do not copy | record the audience problem and the performance clue, then build a distinct explanation and visual treatment. |
| Refresh monthly | a lightweight five-competitor scan is enough in the pilot; automation comes only when it changes decisions. |

## Positioning test

One-sentence position For busy people who want to use AI without drowning in hype, the channel explains important AI changes in plain language, checks the facts, and ends with a practical next step.

| Test | Pass question |
| --- | --- |
| Specificity | Could the right viewer say “this is for me” within five seconds? |
| Difference | Is the promise meaningfully different from generic AI news? |
| Evidence | Can the claim be demonstrated through the content itself? |
| Commercial fit | Do the audience’s problems connect to ethical products or services? |
| Durability | Can the promise survive a quiet news week? |

## Market evidence without false certainty

Do not base the plan on estimated total market size or headline creator-economy growth. The useful market is the number of reachable people who repeatedly value this promise and take a measurable next action. Build the case from channel data, interviews, search questions, newsletter sign-ups, qualified clicks, and partner interest.

A monthly market memo should answer: what questions are rising, which competitors are improving, which offers are appearing, which policies changed, and where audience complaints remain unresolved.

# 3. Brand, trust, and editorial governance

A faceless brand needs more visible proof of judgment, not less. Trust must be designed into the script, media, disclosure, correction, and archive.

## Brand system

| Element | Rule | Fallback |
| --- | --- | --- |
| Name | Clear, ownable, not confusingly close to an existing AI brand. | Use a neutral working name until registration checks pass. |
| Voice | Crisp female American narrator already selected. | Two pre-approved substitutes with documented settings. |
| Visual style | Original illustrated explainers plus controlled screen captures. | Text-led motion graphics when generation fails. |
| Tone | Plain, practical, curious, never alarmist. | Hold any script that needs hype to work. |
| Trust signal | Sources, limits, corrections, and disclosed commercial ties. | Remove the claim or offer if proof is weak. |
| Brand asset record | Fonts, colours, files, licenses, model/version settings. | Rebuild from versioned brand package. |

## Editorial constitution

| Point | Meaning / action |
| --- | --- |
| Allowed | product launches, feature changes, tools, pricing changes, practical concepts, workflows, and comparisons. |
| Not allowed | sensitive or objectionable material, anything involving children, current politics, controversy-led topics, invented expertise, or disguised promotion. |
| Evidence rule | important claims use primary sources when available; uncertain points are labeled; dates and prices are rechecked near publication. |
| Independence rule | sponsor or affiliate status cannot change the factual conclusion, comparison method, or disclosure. |
| Correction rule | material errors trigger rapid review, a visible correction, and unlisting when leaving the item live would mislead. |
| Stale-content rule | never delete by default; update, redirect, trim, remake, or unlist only when fully outdated and misleading. |

## Editorial risk classes

| Class | Examples | Treatment |
| --- | --- | --- |
| Low | Definitions; stable concepts | Normal source check. |
| Medium | Pricing; feature claims; comparisons | Date-stamped source + second check. |
| High | Claims affecting money, security, privacy, or legal choices | Primary source + human review + careful wording. |
| Prohibited | Politics; children; controversial or objectionable topics | Reject at ideation. |

# 4. Content portfolio: balance speed, shelf life, and depth

A news-only feed is fragile; an evergreen-only feed can feel slow. The portfolio should create discovery today, a useful library tomorrow, and raw material for deeper products later.

## Recommended pilot portfolio

| Lane | Share | Purpose | Expiry |
| --- | --- | --- | --- |
| Verified updates | 30% | Timely discovery | Fast |
| Evergreen basics | 30% | Search and trust | Slow |
| Practical demos | 20% | Usefulness and affiliate fit | Medium |
| Comparisons | 10% | Decision support | Medium |
| Recurring series | 10% | Habit and brand memory | Variable |

These percentages are starting assumptions, not promises. The mix changes only after enough videos in each lane allow a fair comparison. One viral item does not prove a lane; one weak item does not kill it.

## Format architecture

| Format | Job | Source asset |
| --- | --- | --- |
| 15–35 second Short | Single fact or decision | One verified claim |
| 35–60 second Short | Explain a change or comparison | Claim set + simple structure |
| 60–90 second platform variant | Deeper TikTok/Instagram test | Extended script |
| 6–12 minute video | Trust, search, revenue depth | Several approved modules |
| Weekly written recap | Owned-audience bridge | Scripts + links + corrections |
| Quarterly guide | Reusable product or lead magnet | Best evergreen modules |

## Topic portfolio rules

| Point | Meaning / action |
| --- | --- |
| No forced quota | if the queue lacks good work, publish less. |
| News expires | assign a publish-by time; after it passes, reframe as analysis or discard. |
| Evergreen reserve | keep at least 14 approved ideas and 5 finished videos before regular cadence. |
| Series earn continuation | a series continues when repeated episodes meet its defined audience and cost threshold. |
| Every topic has a next use | long-form module, email answer, comparison page, guide section, or “no reuse” marker. |
| Winner reuse is not duplication | rebuild the idea for the new format; never simply crop or repost without added value. |

## Long-form is designed from the start

Each Short stores its clean master, script, voice stem, subtitle file, sources, rights status, hook, topic tags, and reuse score. The long-form compiler chooses compatible modules, adds a new argument, transitions, context, and wide-screen visuals. A compilation without new structure is not the target.

The first long-form pilot begins only after enough Shorts expose a real cluster of questions. It should answer one larger question better than the separate Shorts can.

# 5. Production: one item moves through visible gates

The production system should make a bad item stop early, explain why it stopped, and leave a record that improves the next item.

## The standard flow

| Step | Action |
| --- | --- |
| 1 | Collect candidate topics from approved sources and audience questions. |
| 2 | Score fit, freshness, safety, usefulness, evidence, commercial conflict, and duplication. |
| 3 | Create a claim list before writing the script. |
| 4 | Draft the script in plain language; separate fact, interpretation, and recommendation. |
| 5 | Verify every load-bearing claim and save the source record. |
| 6 | Create original visuals or clean screen captures with rights and privacy checks. |
| 7 | Generate voice, subtitles, and platform-safe layout. |
| 8 | Run factual, visual, audio, accessibility, rights, disclosure, and technical checks. |
| 9 | Send the pilot version to the human approval queue. |
| 10 | Publish through a platform adapter; confirm that each post is actually live. |
| 11 | Collect performance, comments, cost, errors, corrections, and revenue events. |
| 12 | Feed only qualified learning back into the controlled knowledge base. |

## Required records per content item

| Record | Minimum contents |
| --- | --- |
| Idea record | Audience problem, lane, freshness, duplicate check |
| Claim record | Claim, source, source date, verification date, risk class |
| Asset manifest | File, creator/tool, license, rights, checksum, storage key |
| QC record | Each gate, result, reviewer, time, repair history |
| Publish record | Platform, post ID, URL, time, status, disclosure flags |
| Performance record | Defined metric windows and source |
| Revenue record | Click, sale, sponsor, confidence: direct/inferred/unknown |
| Lifecycle record | Update, redirect, remake, unlist, sponsor restriction |

## Queue and capacity rules

| Condition | Automatic response |
| --- | --- |
| Review backlog above limit | Stop generation; do not rush approval. |
| Freshness deadline missed | Reframe or discard. |
| Monthly cost forecast above cap | Step down cadence. |
| Provider quota below reserve | Use substitute or evergreen queue. |
| Two repeated technical failures | Quarantine item; escalate. |
| Publishing unverified | Do not mark complete. |
| Free disk below safety floor | Stop renders; archive or clean safe derivatives. |

# 6. Distribution: adapt by platform and build an owned audience

Cross-posting reduces production cost, but each platform has different viewer behaviour, labels, formats, and automation rules. One master can produce several native versions; one identical upload should not be the strategy.

## Role of each channel

| Channel | Primary job | Design implication |
| --- | --- | --- |
| YouTube Shorts | Discovery and topic testing | Strong first second; related long-form path. |
| YouTube long-form | Trust, search, depth, monetization | Complete answer; chapters; reusable evidence. |
| Instagram Reels | Brand memory and sharing | Clean visual identity; caption and profile path. |
| Facebook Reels | Additional reach and older audience test | Plain context; test independently. |
| TikTok | Discovery, search behaviour, native format test | Platform-native edit; do not assume reward eligibility. |
| Email / owned page | Direct audience and durable archive | Useful reason to subscribe; exportable list. |

## Platform adapter rule

The publishing core should hand a finished package to a separate adapter for each platform. The adapter owns format checks, authentication, disclosure fields, retries, post verification, and platform-specific metadata. A policy or API change should require replacing one adapter—not rebuilding the business.

## Organic distribution system

| Point | Meaning / action |
| --- | --- |
| Series and playlists | help a viewer take the next step instead of watching one isolated item. |
| Comments as research | collect recurring questions and objections; never use engagement bait. |
| Cross-links | connect a Short to a useful long-form answer, recap, or comparison rather than a generic home page. |
| Collaborations | begin with complementary educators and tool specialists after the channel has a clear promise and quality record. |
| Search packaging | use the wording real viewers use; avoid titles that promise more than the content delivers. |
| Paid promotion | use only after organic proof; define the spend cap and kill rule before launch. |

## Owned-audience ladder

| Step | Action |
| --- | --- |
| 1 | Start with a simple landing page that explains the promise and has a privacy notice. |
| 2 | Offer a useful, maintainable reason to subscribe: weekly AI changes, beginner glossary, or tool-change tracker. |
| 3 | Collect only the information needed; make consent and unsubscribe clear. |
| 4 | Tag the source at a broad level without invasive tracking. |
| 5 | Export and back up the list on a defined schedule. |
| 6 | Add automation only after the offer earns regular sign-ups and remains useful. |

# 7. Revenue: diversify in a deliberate order

The project should survive if platform advertising pays nothing. Revenue begins only where audience trust and content fit make the offer genuinely useful.

## Revenue ladder

| Stage | Revenue line | Entry test | Main risk |
| --- | --- | --- | --- |
| 1 | Affiliate recommendations | Repeated viewer need + approved program | Biased advice; program changes |
| 2 | Small sponsors | Stable audience + reliable production | Bad fit; slow payment; control clauses |
| 3 | Long-form ads | YPP eligibility + original depth | Platform dependence |
| 4 | Owned guide/template | Repeated problem + support capacity | Low demand; maintenance |
| 5 | Membership/community | Strong return habit + clear recurring value | Ongoing service burden |
| 6 | Licensing / B2B | Reusable IP + rights clarity | Custom-work trap |

## Affiliate operating rules

| Point | Meaning / action |
| --- | --- |
| Fit first | recommend only tools that solve the audience problem and can be explained honestly. |
| Experience evidence | do not imply personal use or results that did not occur. |
| Clear disclosure | put the commercial relationship where the viewer sees the endorsement, not only in a profile or hidden text. |
| Central link registry | one record controls destination, program, country, campaign, effective date, and replacement. |
| Diversification | avoid dependence on one merchant or one product family. |
| Revalidation | check price, terms, availability, and landing page before publication and on a schedule. |

## Sponsor sales system

| Step | Minimum control |
| --- | --- |
| Qualification | Brand fit, product quality, audience relevance, conflict check |
| Proposal | Deliverables, usage rights, schedule, measures, price, exclusions |
| Contract | Payment, cancellation, revisions, claims, disclosure, license, exclusivity |
| Production | Sponsor claims sourced and separated from editorial judgment |
| Approval | Defined response time; no unlimited revisions |
| Publication | Proof of delivery and disclosure captured |
| Payment | Invoice, due date, reminder, late path |
| Closeout | Results, lessons, rights expiry, renewal decision |

## Revenue concentration limits

No platform, sponsor, affiliate program, or product should become irreplaceable. During early proof, concentration may be unavoidable; the plan should record it explicitly and reduce it as alternatives become available. A practical trigger is not a universal percentage: it is the point where losing one source would force the project to stop or break commitments.

# 8. Economics: count cash, time, and delay

A channel can look successful in views and still be a poor business. The plan must show the cost of making, checking, selling, supporting, correcting, and recovering each unit of content.

## Planning assumptions — not quotes or commitments

| Measure | Working range | Use |
| --- | --- | --- |
| Cash cost per Short | $0.45–$1.70 | Capacity planning only |
| Monthly production cash | $50–$170 | About 90 Shorts + 4 long videos |
| Founder review time | 15–30 hours/month | Must be measured in week 1 |
| Media growth | 12–15 GB/month | Archive planning |
| Shorts ad income | $0 in base case | No dependence before real payouts |
| Pilot length | 90 days | Long enough for several controlled cycles |

Important The voice vendor, image vendor, hosting plan, account tiers, and payment fees are not yet locked. Replace estimates with quotations and actual invoices before approving a budget.

## Unit-economics model

| Line | Formula |
| --- | --- |
| Direct content cost | Voice + images + rendering + storage + posting |
| Human cost | Review hours × chosen hourly value |
| Acquisition cost | Promotion spend ÷ qualified new audience actions |
| Contribution | Tracked revenue − direct variable cost |
| True contribution | Contribution − assigned human time − refunds/fees |
| Payback | Acquisition and setup cost ÷ monthly true contribution |
| Runway | Approved cash reserve ÷ monthly net cash burn |

## Three operating scenarios

| Scenario | What happens | Decision |
| --- | --- | --- |
| Slow proof | Weak reach; useful comments; no revenue | Narrow promise; lower cadence; test 30 more items only if learning is clear. |
| Audience proof | Repeat viewers and saves; some qualified clicks | Keep format; add long-form and affiliate proof carefully. |
| Business proof | Repeatable audience; positive true contribution; reliable delivery | Scale one bottleneck at a time; preserve quality gate. |

## Cash-control rules

| Point | Meaning / action |
| --- | --- |
| Monthly ceiling | set before subscriptions or promotion begin; forecast month-end use daily. |
| Cumulative stop-loss | set a maximum total cash loss and a decision date before launch. |
| No annual plan by default | monthly tools until the production method is proven, unless the savings exceed exit risk. |
| Reserve taxes | separate a conservative percentage of every payment until an accountant confirms treatment. |
| Match cash timing | do not count a sale as spendable cash until payout timing and refund exposure are understood. |
| Invoice discipline | sponsor work requires written terms, invoice date, due date, and follow-up owner. |
| Founder time ceiling | if review, sales, or fixes exceed the weekly allowance, reduce cadence before adding tools. |

## Accounting and management records

| Record | Cadence | Decision supported |
| --- | --- | --- |
| Income by source | Per event | Concentration and tax |
| Cost by video/tool | Per event | Contribution and vendor choice |
| Cash forecast | Weekly | Runway and commitments |
| Accounts receivable | Weekly | Sponsor collection |
| Tax reserve | Per payment | Avoid cash surprise |
| Asset and license register | On purchase | Rights and deductions |
| Owner time log | Weekly | True economics |
| Monthly close | Monthly | Continue, change, or pause |

# 9. Tax, legal structure, insurance, and contracts

These items are not paperwork for later. They determine who owns the work, who owes tax, who can sign, what can be promised, and what happens when a claim or payment goes wrong.

## Canadian tax and business setup

| Point | Meaning / action |
| --- | --- |
| Income | the Canada Revenue Agency treats income-producing social-media activity as business activity; cash and non-cash benefits need records. |
| GST/HST | the federal small-supplier threshold is generally $30,000 in taxable supplies over a single quarter or four consecutive calendar quarters; exact place-of-supply treatment needs professional review. |
| Bookkeeping | keep platform statements, invoices, fees, foreign exchange, equipment, subscriptions, contractor payments, and benefit-in-kind records. |
| Structure | beginning as a sole proprietor may be simple, but incorporation should be reconsidered when profit, liability, ownership, or contracting needs justify it. |
| Cross-border | platform and sponsor payments may involve foreign tax forms, withholding, sales-tax rules, and foreign exchange. Confirm before the first material payment. |
| Professional trigger | use a Canadian accountant before GST/HST registration, incorporation, a cross-border sponsor contract, or a material product launch. |

## Contract library

| Agreement | Must answer |
| --- | --- |
| Sponsor | Deliverables; approvals; claims; payment; cancellation; usage; exclusivity; disclosure |
| Contractor | Scope; confidentiality; security; IP assignment; warranties; deletion; termination |
| Affiliate | Allowed promotion; disclosure; trademarks; prohibited traffic; payment; termination |
| Software/vendor | Commercial rights; data use; model training; retention; exit/export; liability |
| Collaboration | Ownership; credits; channels; revenue; approvals; removal |
| License | Media, territory, term, edits, sublicensing, archive and reuse |

## Insurance decision

| Cover to discuss | Why it may matter | Trigger for quote |
| --- | --- | --- |
| Commercial general liability | Basic third-party claims | First meaningful sponsor or physical event |
| Media / errors and omissions | Defamation, copyright, content-error claims | Regular sponsored or higher-risk claims |
| Cyber / privacy | Breach response and data incidents | Email list, customer accounts, or contractor access |
| Equipment | Loss or damage to production devices | Replacement cost would interrupt operations |

Insurance terms vary and exclusions matter. A broker should review the actual content, automation, territory, revenue, contractors, and use of artificial intelligence. Buying a policy without checking exclusions can create false comfort.

## Intellectual-property chain

| Asset | Proof to retain |
| --- | --- |
| Script | Draft history, sources, author/tool record, final approval |
| Generated image/video | Provider, plan, terms date, prompt/job ID, output file |
| Voice | License tier, cloned/stock status, commercial rights, settings |
| Music/sound | License, territory, platform, term, attribution |
| Screen capture | Account used, private-data scan, product-mark treatment |
| Font/template | License file and permitted commercial uses |
| Contractor work | Signed assignment and underlying-license list |

## Privacy and data minimization

| Point | Meaning / action |
| --- | --- |
| Collect less | do not retain viewer or customer data that the business does not need. |
| Separate capture profile | screen recordings use a clean account, synthetic examples, hidden notifications, and no personal files. |
| Control access | roles get the minimum needed; shared passwords are prohibited; access is removed promptly. |
| Retention schedule | define how long leads, customers, comments, logs, raw captures, support messages, and backups remain. |
| Consent and notice | the landing page and mailing list explain collection, use, providers, unsubscribe, and contact route. |
| Incident plan | contain, preserve evidence, assess impact, notify required parties, keep breach records, and repair the cause. |
| Do not scrape by default | platform data collection must fit law, terms, consent, and actual business need. |

## Accessibility baseline

| Area | Minimum standard |
| --- | --- |
| Captions | Accurate, timed, readable, corrected—not auto-caption text accepted blindly. |
| On-screen text | Large enough, high contrast, sufficient display time, safe margins. |
| Audio | Clear speech; music does not mask words; avoid sudden volume jumps. |
| Visual meaning | Do not communicate essential meaning by colour alone. |
| Web/email | Meaningful links, headings, alt text, keyboard-friendly forms. |
| Language | Plain words; explain unavoidable technical terms. |

# 10. Platform policy and disclosure controls

Platform rules change and enforcement can be uneven. Store the rule, the date checked, the account scope, and the content decision. Recheck before implementing an automation or monetization feature.

## Current high-level controls

| Area | Control |
| --- | --- |
| Originality | Substance must vary and deliver value; do not mass-produce interchangeable templates. |
| Synthetic media | Label realistic synthetic or meaningfully altered depictions when the platform requires it. |
| Commercial relationship | Disclose material connections clearly in the content and nearby text. |
| Upload automation | Use supported APIs; test account/project restrictions; verify the result live. |
| Monetization | Treat published thresholds as eligibility gates, not approval guarantees. |
| Community rules | Topic and visual guardrails run before generation and again before publishing. |
| Account actions | Keep evidence, roles, two-step security, recovery methods, and appeal package current. |

## Disclosure decision record

| Question | Example response |
| --- | --- |
| Is the media synthetic or altered? | Yes / no / uncertain |
| Could it look like a real person/event/place? | Describe risk |
| Is there a material connection? | Affiliate, sponsor, gift, employee, other |
| What must appear in-video? | Plain disclosure wording |
| What platform setting is required? | Platform-specific field |
| Who approved the final disclosure? | Name and time |
| What rule version was used? | URL and checked date |

Implementation rule A live official help page controls over any number printed in this plan. Thresholds, labels, API quotas, and eligibility rules must be rechecked immediately before implementation.

# 11. Technology architecture: modular, replaceable, observable

The system should not depend on one tool, one model, one machine, or one person. Separate pipelines prevent a failure in promotion or reporting from stopping content creation.

## Five independent pipelines

| Pipeline | Owns | Does not own |
| --- | --- | --- |
| Create and publish | Topics, scripts, assets, QC, review, posting | Cross-business reports |
| Promotion | Campaigns, spend controls, creative variants | Organic production |
| Housekeeping | Stale content, links, ledgers, archive checks | Performance interpretation |
| Performance monitoring | Shared measures, R1/R2/R3 reports, anomalies | Revenue optimization actions |
| Earnings improvement | Attribution, affiliate tests, sponsor funnel | Editorial approval |

The only shared operational asset is the learning knowledge base, and access to it is controlled. Each pipeline has its own codebase, configuration, job history, failure log, health checks, recovery procedure, and deployment path.

## Layered design

| Layer | Purpose | Change isolation |
| --- | --- | --- |
| Policy/configuration | Guardrails, thresholds, cadence, provider choices | Change behaviour without changing code |
| Core workflow | Stable business steps and state transitions | Provider-neutral |
| Adapters | Platform, model, storage, analytics connections | Replace one service |
| Data layer | Records, versions, lineage, retention | Independent of user interface |
| Observability | Logs, metrics, alarms, incident record | External check of internal system |
| Control surface | Approve, pause, retry, quarantine, manual mode | Human authority |

## State machine for every item

Use explicit states such as proposed, researching, blocked, scripted, assets ready, QC failed, awaiting approval, approved, scheduled, publishing, live, verified, correction required, unlisted, and archived. A state change records who or what changed it, why, when, and which version. This prevents “almost published” work from appearing complete.

## No silent success

| Point | Meaning / action |
| --- | --- |
| Publishing success | the platform returns an identifier and an independent check confirms the expected post is live. |
| Backup success | the copy exists, can be read, and a restore test succeeds. |
| Healing success | the original business outcome is verified—not merely that a retry returned no error. |
| Report success | data coverage and freshness are shown; missing sources do not become zeros. |
| Approval success | the exact version approved is the exact version published. |

## Security baseline

| Control | Rule |
| --- | --- |
| Credentials | Use an approved secret store; never put secrets in code, logs, prompts, or media. |
| Two-step security | Enable on owner and recovery accounts; store recovery methods safely. |
| Least privilege | Separate read, create, approve, and publish authority where practical. |
| Environment separation | Test accounts and sandbox data must not publish publicly. |
| Dependency hygiene | Pin versions; scan updates; maintain a component list. |
| Logs | Remove private data and secrets; limit retention and access. |
| Emergency control | “Pause all publishing now” stops every outward publishing path. |

# 12. Data, storage, backup, and recovery

Data becomes an asset only when it is understandable, portable, protected, and recoverable.

## Data classes

| Class | Examples | Treatment |
| --- | --- | --- |
| Public | Published videos, public captions | Archive and integrity checks |
| Internal | Scripts, prompts, tests, analytics | Access control and backup |
| Confidential | Contracts, rates, unreleased plans | Restricted, encrypted, minimal sharing |
| Sensitive | Credentials, tax and personal data | Approved protected systems only; strict retention |
| Disposable | Render cache, temporary derivatives | Automatic expiry after verification |

## Version and lineage

Every final video must be traceable backward to the approved script, source set, media inputs, model or tool versions, settings, rights record, and reviewer. Metrics must be traceable to the platform, collection time, time zone, and definition. A later correction creates a new version; it does not erase the history.

## 3-2-1 recovery pattern

| Point | Meaning / action |
| --- | --- |
| Three copies | working copy plus two independent copies. |
| Two types of storage | for example local working storage and object/cloud storage. |
| One off-machine or isolated copy | protected from device loss, malware, or operator error. |
| Test, do not assume | restore selected code, records, and media quarterly; run a fuller rebuild twice a year. |
| Document targets | set recovery point (how much recent work may be lost) and recovery time (how long service may be down) for each pipeline. |

## Suggested recovery targets for the pilot

| Asset | Recovery point | Recovery time | Method |
| --- | --- | --- | --- |
| Code/config | After every approved change | 4 hours | Private version control + rebuild guide |
| Business records | Daily | 8 hours | Encrypted backup + export |
| Source/media | Daily | 24 hours | Off-machine archive + second copy |
| Credentials | After change | 4 hours | Protected store + tested recovery owner |
| Published catalog | Weekly index | 48 hours | Platform export + local publish record |

These are proposed targets BalRam should decide whether these recovery windows match the cost and urgency of the pilot. Tighter recovery normally costs more.

# 13. Quality assurance and release governance

Quality is a series of gates with evidence, not one final “looks good” check.

## Release gates

| Gate | Checks | Veto owner |
| --- | --- | --- |
| Topic | Scope, sensitivity, duplicate, freshness, usefulness | Editorial |
| Claims | Source quality, dates, prices, limitations, wording | Fact review |
| Script | Plain language, promise, accuracy, no disguised promotion | Editorial |
| Visual | Meaning match, private-data scan, unsafe frames, logos | Visual QC |
| Audio | Correct words, pronunciation, loudness, artifact scan | Media QC |
| Rights | Every asset and tool has commercial-use evidence | Rights owner |
| Disclosure | AI/commercial labels are complete and visible | Compliance |
| Technical | Dimensions, duration, captions, file, safe margins | Technical QC |
| Human approval | Final exact version approved during pilot | BalRam |
| Live proof | Expected title/media/disclosure visible on platform | Publisher |

## Independent checks where errors matter most

| Point | Meaning / action |
| --- | --- |
| Numbers and dates | recompute or compare with a second path. |
| Privacy | scan all frames, not a single thumbnail. |
| Rights | check the actual account tier and dated terms, not a product marketing page. |
| Platform state | read the live post and compare it with the approved manifest. |
| Recovery | restore into a clean location and run the recovered workflow. |
| Financial reporting | reconcile payouts to platform statements and bank receipts. |
| Automated tests | include deliberate bad examples so the gate proves it can fail. |

## Change approval levels

| Level | Examples | Approval |
| --- | --- | --- |
| Routine | Typo correction; failed bounded retry | Pipeline owner |
| Controlled | Prompt, model, visual template, metric threshold | Documented test + owner |
| Material | New platform, paid spend, affiliate program, sponsor, data collection | BalRam |
| Critical | Review removal, auto-publish, guardrail change, credential model | Explicit “go auto” / “lock the vision” or named approval |

## Correction and recall

A material factual error, rights complaint, privacy exposure, misleading commercial claim, or unsafe output triggers the pause path. Preserve evidence, stop further distribution where possible, assess related items, correct visibly, unlist when the content is fully outdated and misleading, inform affected partners where required, and record the prevention change. Never delete merely to hide the history.

# 14. Self-improvement: learn without chasing noise

The business improves through controlled experiments, a shared record, and explicit promotion rules—not by automatically copying whatever got the most views yesterday.

## Experiment method

| Step | Action |
| --- | --- |
| 1 | Write the question and decision before starting. |
| 2 | Choose one primary measure and guardrails such as trust, cost, and negative feedback. |
| 3 | Change one main variable when practical. |
| 4 | Use comparable content or randomized release slots where possible. |
| 5 | Wait for the pre-set sample and measurement window. |
| 6 | Record result, uncertainty, and confounders. |
| 7 | Promote only if the improvement repeats and does not harm a guardrail. |
| 8 | Set an expiry date; revalidate because platform behaviour changes. |

## Learning tiers

| Tier | Evidence | Use |
| --- | --- | --- |
| Observation | One or two items | Create a hypothesis only |
| Candidate | Several comparable items | Run a controlled test |
| Validated | Repeat test; meaningful lift; guardrails pass | Use in one pipeline |
| Standard | Survives later recheck | Default with version |
| Retired | No longer works or violates policy | Keep history; stop use |

## What the shared knowledge base stores

| Record | Key fields |
| --- | --- |
| Audience insight | Problem, exact wording, evidence, segment, date |
| Content learning | Hypothesis, variant, measure, sample, result, confidence |
| Failure pattern | Symptom, cause, detection, fix, recurrence |
| Policy fact | Platform, rule, URL, checked date, owner, next check |
| Vendor fact | Capability, cost, limit, terms date, substitute |
| Decision | Choice, reason, owner, effective date, review date |
| Correction | Affected item, impact, action, prevention |

## Anti-gaming rules

| Point | Meaning / action |
| --- | --- |
| Do not optimize only for views | include satisfied watch, return behaviour, trust signals, and business action. |
| Do not hide failures | failed experiments remain in the record. |
| Do not change definitions mid-test | metric meaning and window are versioned. |
| Do not promote automatically from tiny samples | insufficient evidence stays a hypothesis. |
| Do not let commercial conversion overrule trust | refunds, complaints, disclosure, and audience harm are guardrails. |

# 15. Self-healing, incidents, and continuity

Self-healing means a known failure can be contained and recovered within limits. It does not mean endless retries or unsupervised changes.

## Bounded healing pattern

| Step | Action |
| --- | --- |
| 1 | Detect the failed business outcome, not only the error code. |
| 2 | Classify severity and affected scope. |
| 3 | Stop outward actions if safety, rights, privacy, money, or reputation may be harmed. |
| 4 | Retry only known temporary failures, with a small limit and increasing delay. |
| 5 | Switch to an approved substitute when the failure class allows it. |
| 6 | Quarantine the item after the budget is exhausted. |
| 7 | Alert with the evidence, current state, and safe next action. |
| 8 | Verify recovery independently and add the learning to the failure record. |

## Severity and response

| Level | Example | Response |
| --- | --- | --- |
| S1 Critical | Public privacy leak; account takeover; unsafe publication | Immediate global pause; human incident lead |
| S2 High | Wrong video/title; rights complaint; large cost anomaly | Stop affected pipeline; contain and review |
| S3 Medium | Repeated provider failure; stale queue; missing metrics | Fallback or manual mode; same-day review |
| S4 Low | One retryable job or cosmetic issue | Bounded retry; log |

## Manual modes

| Failure | Manual route |
| --- | --- |
| Topic service unavailable | Select from reviewed evergreen reserve |
| Writing/model failure | Use approved template and human draft |
| Image generation failure | Use original typography/diagrams/screen capture |
| Voice service failure | Use backup voice or publish an approved no-voice format |
| Scheduler/API failure | Upload manually from approved package |
| Analytics failure | Use platform export; mark coverage gap |
| Email system failure | Pause sends; keep sign-up consent and export safe |

## Business continuity if BalRam is unavailable

| Point | Meaning / action |
| --- | --- |
| Default state | publishing remains paused unless an authorized successor has written authority and operating access. |
| Continuity packet | plain-language system map, contacts, accounts, renewal dates, contracts, recovery steps, emergency commands, and current obligations. |
| Authority map | who may pause, pay, approve, publish, access data, or speak to a sponsor. |
| Recurring obligations | tax, invoices, sponsor live periods, subscriptions, storage, domains, and privacy requests. |
| Quarterly walkthrough | another authorized person should be able to locate the packet and execute a safe pause without revealing credentials. |

# 16. Organization, capacity, and decision rights

The system should not hide founder work. Every recurring task needs an owner, a backup, a capacity assumption, and a point where specialist help becomes cheaper than risk.

## Core roles — one person may hold several early on

| Role | Accountability | Specialist trigger |
| --- | --- | --- |
| Business owner | Budget, positioning, stop-loss, material changes | Incorporation, financing, acquisition |
| Editorial owner | Audience promise, calendar, corrections | Volume exceeds review capacity |
| Fact reviewer | Claim evidence and wording | High-stakes financial/legal/security claims |
| Production owner | Assets, versions, handoff | Backlog or error rate persists |
| Rights/privacy owner | Licenses, disclosures, privacy requests | Complaint, data incident, complex license |
| Platform operator | Accounts, publishing, recovery | Access, API, or appeal problem |
| Revenue owner | Offers, affiliates, sponsors, collection | Large/complex contract or unpaid balance |
| Technical owner | Code, monitoring, backup, recovery | Security event or architectural change |
| Bookkeeper/accountant | Books, tax, reconciliation | Before registration/incorporation/cross-border complexity |
| Lawyer/insurance broker | Contracts, rights, coverage | Material sponsor, claim, hiring, or product risk |

## Decision-rights rule

For each recurring process, name who proposes, who decides, who executes, who checks, and who must only be informed. The person who creates an asset should not be the only person or automated check that clears its highest-risk claim. During the pilot, BalRam retains final publication approval.

## Capacity model

| Capacity | Measure | Protective trigger |
| --- | --- | --- |
| Research | Topics fully sourced/week | Queue falls below two weeks |
| Review | Minutes/item and backlog age | Oldest item exceeds deadline |
| Production | Passed items/day | Error or rework trend rises |
| Support | Questions/complaints/week | Response promise at risk |
| Sales | Qualified partners/month | Follow-up or invoices slip |
| Technical | Incidents and recovery hours | Maintenance exceeds feature work |
| Cash | Forecast end balance | Stop-loss or reserve floor approached |

## Hiring and outsourcing order

| Step | Action |
| --- | --- |
| 1 | Remove unnecessary work and automate safe repetition. |
| 2 | Document the process and quality evidence. |
| 3 | Outsource a narrow output with a paid test and explicit acceptance standard. |
| 4 | Give minimum access; keep source files and rights records. |
| 5 | Measure rework, speed, cost, and reliability—not only hourly rate. |
| 6 | Expand only after the contractor can be replaced and the knowledge remains with the business. |

# 17. Three-phase roadmap

Each phase has an outcome, dependencies, exit gates, and work that stays deliberately out of scope.

## Phase 1 — prove trust and demand

Goal Produce a small, reliable body of original work that a defined audience finds useful, while proving review, recovery, and cost control. Suggested horizon: first 90 days.

| Build | Dependency | Exit proof |
| --- | --- | --- |
| Brand name and base identity | Conflict search + registration/handle decisions | Assets and rights recorded |
| Clean accounts and security | Owner access + recovery plan | Access/recovery test passes |
| Source and claim ledger | Editorial policy | Every pilot claim traceable |
| Original media workflow | Rights decisions | Five consecutive QC passes |
| 14-topic evergreen reserve | Audience promise | Two weeks of safe fallback |
| Manual multi-platform pilot | Approved packages | Posts verified live |
| Basic metrics and cost ledger | Platform access | Complete defined windows |
| Backup and rebuild guide | Storage decision | Restore test succeeds |
| Audience interview/test loop | Target segment | One problem cluster shows repeat interest |

### Phase 1 does not include

| Point | Meaning / action |
| --- | --- |
| 1 | Automatic public publishing. |
| 2 | Three-posts-per-day obligation. |
| 3 | Paid audience growth. |
| 4 | Multiple niches or languages. |
| 5 | Membership, course, or merchandise. |
| 6 | Material sponsor commitments. |

## Phase 2 — prove repeatability and revenue

Goal Show that one or more formats can repeat with controlled cost, reliable quality, and an ethical revenue signal. Suggested horizon: months 4–9, only after Phase 1 exit gates.

| Build | Dependency | Exit proof |
| --- | --- | --- |
| Reliable scheduled publishing | Phase 1 live verification history | Low incident/rework rate |
| Weekly long-form pilot | Question cluster + modules | Repeat viewing and meaningful depth |
| Affiliate pilot | Audience need + disclosure/legal review | Qualified clicks and reconciled payout |
| Sponsor readiness | Audience evidence + rate card + contract | One controlled paid pilot or clear no-fit decision |
| Owned-audience offer | Useful repeatable resource + privacy notice | Steady opt-in and low unsubscribe/complaint rate |
| Automated housekeeping | Stable lifecycle rules | Monthly review completes accurately |
| Formal incident drills | Runbooks + backup roles | Recovery within approved targets |
| Capacity decision | Measured owner time | Hire, reduce cadence, or automate safely |

## Phase 3 — scale proven units

Goal Increase reach and income without weakening trust, recoverability, or contribution. No calendar promise: begin only when Phase 2 evidence passes.

| Scale option | Dependency | Kill/rollback trigger |
| --- | --- | --- |
| Higher cadence | Positive true contribution + spare review capacity | Rework or trust measure worsens |
| Paid promotion | Organic winner + attribution | Cost exceeds cap |
| Second platform emphasis | Native evidence + adapter reliability | No incremental quality audience |
| Second niche | First niche playbook + separate audience case | Dilution or weak economics |
| Second language | Translation/cultural QA + commercial case | Quality gap or support overload |
| Owned product | Repeated problem + support/refund plan | Weak demand or high burden |
| Team | Documented role + cash runway | Work not actually delegable |
| Selective auto-publish | Long stable history + explicit approval | Any critical gate failure |

# 18. Dependency map and critical path

The dependency map prevents expensive downstream work from starting on unstable foundations.

| Before this… | These must be true |
| --- | --- |
| Choose permanent brand assets | Name conflict screen, registration/handle check, identity decision |
| Open platform accounts | Owner identity/access plan, two-step security, recovery method |
| Generate media at scale | Commercial rights, cost cap, backup provider, asset manifest |
| Publish a pilot | Editorial scope, claim ledger, QC, approval, account security, backup |
| Use API publishing | Manual flow stable, developer project approved, private-test success, live verification |
| Add affiliate links | Audience need, program acceptance, disclosure, link registry, tax record |
| Sign a sponsor | Audience proof, rate card, contract, claims process, invoicing, insurance review |
| Collect email | Useful offer, privacy notice, consent, unsubscribe, retention, export |
| Create long-form | Validated question cluster, reusable modules, new narrative, separate QC |
| Remove review gate | Long stable record, tested auto-stops, recovery drill, explicit approval |
| Hire/contract | Documented role, budget, agreement, access plan, acceptance test |
| Launch a product | Repeated demand, rights, terms, support, refunds, tax, cash plan |
| Enter another niche/language | First channel playbook, capacity, separate market case, cultural/editorial QA |

## Critical path

| Step | Action |
| --- | --- |
| 1 | Set the audience promise and boundaries. |
| 2 | Choose a workable name and establish secure ownership. |
| 3 | Create the evidence, rights, and content records. |
| 4 | Build and test one end-to-end manual package. |
| 5 | Prove the review and live-verification gates. |
| 6 | Build the evergreen reserve and measure real capacity. |
| 7 | Publish a limited pilot and complete defined measurement windows. |
| 8 | Decide whether audience proof justifies Phase 2. |

## Decisions BalRam must make before launch

| Decision | Recommended default | Deadline |
| --- | --- | --- |
| Brand name | Do not rush; use working name internally | Before public accounts |
| Pilot pace | 1–2 strong Shorts/day, 5 days/week | Before reserve build |
| Monthly cash cap | Use low end until actual cost is measured | Before paid tools |
| Cumulative stop-loss | An amount affordable to lose fully | Before launch |
| Founder time cap | Fixed weekly window | Before regular cadence |
| Affiliate categories | Only tools with clear audience fit | Before any link |
| Business/tax setup | Confirm with Canadian accountant | Before material revenue |
| Continuity backup | One trusted, authorized person or explicit pause-only plan | Before scale |

# 19. Risk and contingency register

Each risk has an early signal, prevention, fallback, owner, phase, dependency, and the part that remains after controls.

| Risk | Early trigger | Prevention | Fallback |
| --- | --- | --- | --- |
| Wrong or outdated claim | Correction signals; source conflict | Claim ledger; freshness clock | Pause/correct/unlist |
| Interchangeable AI content | Low satisfaction; policy warning | Material variation; human judgment | Stop format; rebuild |
| Unsafe or off-scope topic | Classifier uncertainty; reviewer flag | Hard scope rules; manual route | Reject; pause related queue |
| Private data in capture | Frame scan or complaint | Clean profile; synthetic data | Remove; incident response |
| Unlicensed asset | Missing manifest; complaint | Approved asset library; evidence | Replace; take down if needed |
| Missing AI/ad disclosure | QC fail; platform notice | Disclosure decision record | Edit/repost; notify partner |
| Poor visual/claim match | QC mismatch; negative comments | Scene-to-sentence check | Replace scene; correct |
| Voice/image provider outage | Errors; quota low | Backup provider; cached settings | No-voice/text-led format |
| Publishing failure | No live proof; wrong metadata | Adapter tests; idempotency | Manual upload; pause retry |
| Account takeover | Login alert; access change | 2FA; least privilege; recovery | Global pause; recover; appeal |

| Risk | Owner | Phase | Dependency | Residual risk |
| --- | --- | --- | --- | --- |
| Wrong or outdated claim | Editorial | 1 | Source system | Residual: sources can be wrong |
| Interchangeable AI content | Editorial | 1 | Portfolio rules | Residual: platform judgment |
| Unsafe or off-scope topic | Editorial | 1 | Guardrails | Residual: ambiguous cases |
| Private data in capture | Privacy | 1 | Capture workflow | Residual: missed frame |
| Unlicensed asset | Rights | 1 | Rights register | Residual: disputed terms |
| Missing AI/ad disclosure | Compliance | 1 | Policy registry | Residual: rule ambiguity |
| Poor visual/claim match | Production | 1 | Visual QC | Residual: interpretation |
| Voice/image provider outage | Production | 1 | Adapters | Residual: simultaneous outage |
| Publishing failure | Platform | 1 | Approved package | Residual: platform outage |
| Account takeover | Owner | 1 | Secure accounts | Residual: recovery delay |

# Risk register — business and market

| Risk | Early trigger | Prevention | Fallback |
| --- | --- | --- | --- |
| No audience fit | Weak return/saves across fair test | Interviews; narrow promise | Reposition or stop |
| News treadmill | Queue expiry; burnout | Evergreen reserve; mix rule | Reduce cadence |
| Founder bottleneck | Approval age rises | Time cap; queue limit | Auto-hold; delegate later |
| Costs creep | Forecast crosses cap | Per-unit and monthly ceilings | 3→2→1 cadence cut |
| Revenue never appears | No qualified clicks/partners | Zero-ad base case; staged offers | Stop or hobby-scale |
| One income source dominates | Loss would stop business | Diversify programs/offers | Cut costs; substitute |
| Sponsor harms trust | Audience concern; claim conflict | Fit screen; editorial independence | Decline/terminate/correct |
| Late sponsor payment | Invoice overdue | Deposit/milestones; terms | Pause work; collection path |
| Adverse cash timing | Earned but unpaid; tax due | Weekly forecast; reserves | Delay spend; reduce cadence |
| Affiliate program changes | Commission/terms change | Program diversification | Replace links/offer |
| Competitor imitation | Format copied | Evidence, brand, owned audience | Deepen value; do not race volume |
| Reputation incident | Complaint spike; false narrative | Evidence, corrections, response owner | Pause; factual response |

| Risk | Owner | Phase | Dependency | Residual risk |
| --- | --- | --- | --- | --- |
| No audience fit | Owner | 1 | Measurement | Residual: noisy data |
| News treadmill | Editorial | 1 | Portfolio | Residual: quiet weeks |
| Founder bottleneck | Owner | 1 | Capacity model | Residual: absence |
| Costs creep | Finance | 1 | Cost ledger | Residual: price changes |
| Revenue never appears | Owner | 2 | Audience proof | Residual: weak buying intent |
| One income source dominates | Revenue | 2 | Attribution | Residual: early concentration |
| Sponsor harms trust | Owner | 2 | Contract | Residual: perception |
| Late sponsor payment | Finance | 2 | Contract/invoice | Residual: default |
| Adverse cash timing | Finance | 1 | Bookkeeping | Residual: platform holds |
| Affiliate program changes | Revenue | 2 | Link registry | Residual: sudden termination |
| Competitor imitation | Owner | 2 | Learning base | Residual: commodity topics |
| Reputation incident | Owner | 1 | Incident plan | Residual: amplification |

# Risk register — technology, legal, and continuity

| Risk | Early trigger | Prevention | Fallback |
| --- | --- | --- | --- |
| Code loss or bad release | Build fails; unexpected change | Private version control; tests | Rollback; clean rebuild |
| Media/data loss | Missing/corrupt files | 3-2-1 copies; checksums | Restore from isolated copy |
| Backup not usable | Restore drill fails | Automated verification; drills | Rebuild priority set |
| Secret exposure | Alert; secret in log/code | Vault; scanning; redaction | Revoke/rotate; incident review |
| Dependency compromise | Scan alert; abnormal behaviour | Pin/scan/minimize components | Isolate; rollback; replace |
| Runaway retry/spend | Error loop; cost spike | Retry/cost budgets; circuit breaker | Kill job; manual mode |
| Bad learning feedback | Quality drops after promotion | Evidence tiers; canaries | Rollback rule/version |
| Analytics gap/misread | Missing data; metric change | Definitions; coverage indicator | Manual export; mark unknown |
| Privacy breach | Unexpected access/disclosure | Minimize; restrict; retain briefly | Contain; assess; notify/record |
| Tax non-compliance | Threshold/revenue approaches | Records; calendar; accountant | Correct filings and controls |
| Contract/rights dispute | Complaint or conflicting term | Written terms; rights chain | Counsel; pause affected use |
| Insurance gap | Claim excluded or uninsured | Broker review and exclusions check | Reserve/contain/legal help |
| Platform suspension/loss | Warning; access removal | Policy file; secure access; appeal kit | Appeal; owned audience; alternatives |
| Owner unavailable | Approvals and bills stall | Continuity packet; backup authority | Pause safely; successor route |
| Vendor exit/price shock | Notice or quota change | Adapter; export; substitute test | Migrate; reduce cadence |

| Risk | Owner | Phase | Dependency | Residual risk |
| --- | --- | --- | --- | --- |
| Code loss or bad release | Tech | 1 | Repository | Residual: hidden dependency |
| Media/data loss | Tech | 1 | Storage | Residual: backup corruption |
| Backup not usable | Tech | 1 | Runbook | Residual: recovery delay |
| Secret exposure | Security | 1 | Access model | Residual: misuse before revoke |
| Dependency compromise | Tech | 2 | Component list | Residual: unknown flaw |
| Runaway retry/spend | Tech | 1 | Monitoring | Residual: delayed alert |
| Bad learning feedback | Learning | 2 | Experiment log | Residual: regime change |
| Analytics gap/misread | Performance | 1 | Platform access | Residual: opaque algorithm |
| Privacy breach | Privacy | 2 | Incident plan | Residual: legal cost |
| Tax non-compliance | Finance | 1 | Books | Residual: interpretation |
| Contract/rights dispute | Owner | 2 | Contract library | Residual: dispute cost |
| Insurance gap | Owner | 2 | Risk profile | Residual: exclusions |
| Platform suspension/loss | Owner | 1 | Account records | Residual: lost reach |
| Owner unavailable | Owner | 2 | Authority map | Residual: prolonged absence |
| Vendor exit/price shock | Tech | 1 | Provider registry | Residual: migration loss |

## Risk acceptance rule

A control never removes all risk. The owner must explicitly accept, reduce, transfer, avoid, or postpone each material residual risk. “We have a tool for it” is not acceptance. The decision record should say what loss remains possible, why that is acceptable now, and when it will be reviewed.

# 20. Scorecard and management rhythm

A balanced scorecard prevents reach from hiding weak trust, bad economics, operational fragility, or owner overload.

## Five measure groups

| Group | Core measures | Decision |
| --- | --- | --- |
| Leading | Approved idea reserve; research age; review backlog; production cycle | Can we deliver safely? |
| Audience | Viewed vs swiped; satisfied watch; completion; saves; shares; repeat viewers | Is the work useful? |
| Business | Qualified clicks; leads; sponsor pipeline; cash received; contribution | Is there a business? |
| Reliability | QC pass; publish verification; incidents; recovery; cost anomalies | Can it operate? |
| Trust | Corrections; complaints; disclosure failures; unlist reasons; unsubscribe | Are we preserving permission? |

## Metric discipline

| Point | Meaning / action |
| --- | --- |
| Definition first | record numerator, denominator, time window, time zone, source, and exclusions. |
| Cohorts | compare content at the same age; do not compare a 30-day item with a 24-hour item. |
| Coverage | show missing accounts or delayed data; do not turn missing into zero. |
| Confidence | small samples get wider uncertainty and fewer decisions. |
| Business connection | a metric remains only if it informs a real choice. |
| Versioning | when a platform changes a definition, start a new series or mark the break. |

## Operating cadence

| Cadence | Review |
| --- | --- |
| Per item | Gates, publish proof, immediate incident/correction |
| Daily during pilot | Queue, freshness, failures, spend forecast |
| Weekly | Audience learning, cost, founder time, experiments, partner actions |
| Monthly | Close books, risks, stale content, link check, platform policy, portfolio mix |
| Quarterly | Strategy, restore drill, vendor alternatives, insurance/legal/tax triggers |
| Phase gate | Evidence against exit criteria; continue, change, pause, or stop |

## R1 / R2 / R3 reporting

| Report | Purpose | Audience |
| --- | --- | --- |
| R1 — Alert | Immediate exception with safe action | Responsible operator |
| R2 — Weekly operating view | Progress, bottlenecks, experiments, cash | BalRam + operators |
| R3 — Phase review | Evidence, economics, risks, strategic decision | BalRam + advisers as needed |

# 21. Implementation backlog

This backlog turns the plan into ordered work. “Keep” means build in the named phase; “Park” means preserve the idea without spending now; “Decide” means owner input is required first.

## Foundation and pilot

| Item | Status | P | Dependency | Owner |
| --- | --- | --- | --- | --- |
| Audience promise | Keep | 1 | None | Owner |
| Brand name and legal/conflict check | Decide | 1 | Audience promise | Owner |
| Brand asset/rights package | Keep | 1 | Name | Editorial |
| Editorial constitution | Keep | 1 | Audience promise | Editorial |
| Source and claim ledger | Keep | 1 | Editorial policy | Fact review |
| Topic safety filter | Keep | 1 | Guardrails | Editorial |
| 14-topic evergreen reserve | Keep | 1 | Audience promise | Editorial |
| Clean capture profile | Keep | 1 | Security baseline | Production |
| Asset manifest | Keep | 1 | Rights policy | Rights |
| Voice and visual fallback | Keep | 1 | Approved brand | Production |
| Per-item QC record | Keep | 1 | Gate definitions | QC |
| Human approval queue | Keep | 1 | Exact version control | BalRam |
| Manual platform posting | Keep | 1 | Secure accounts | Platform |
| Live-post verification | Keep | 1 | Publish record | Platform |
| Cost and time ledger | Keep | 1 | Budget cap | Finance |
| Backup and rebuild guide | Keep | 1 | Storage/repository | Tech |
| Restore drill | Keep | 1 | Backup | Tech |
| Incident pause control | Keep | 1 | Authority map | Tech |
| Basic scorecard | Keep | 1 | Metric definitions | Performance |

# Implementation backlog — repeatability and revenue

| Item | Status | P | Dependency | Owner |
| --- | --- | --- | --- | --- |
| Platform adapters | Keep | 2 | Manual flow stable | Tech |
| Automated policy recheck calendar | Keep | 2 | Policy registry | Compliance |
| Weekly long-form pilot | Keep | 2 | Validated question cluster | Editorial |
| Owned landing page | Keep | 2 | Brand + privacy notice | Owner |
| Useful email offer | Decide | 2 | Repeated audience problem | Editorial |
| Affiliate pilot | Decide | 2 | Program/legal/tax/disclosure | Revenue |
| Sponsor rate card | Keep | 2 | Audience evidence | Revenue |
| Sponsor contract template | Keep | 2 | Lawyer trigger | Owner |
| Invoice/receivable workflow | Keep | 2 | Bookkeeping | Finance |
| Housekeeping automation | Keep | 2 | Stable lifecycle rules | Tech |
| Attribution model | Keep | 2 | Revenue events | Performance |
| Formal recovery drills | Keep | 2 | Runbooks | Tech |
| Contractor pilot | Decide | 2 | Measured bottleneck | Owner |
| Paid promotion | Park | 2 | Organic proof + cap | Promotion |
| Insurance purchase | Decide | 2 | Broker quote + risk profile | Owner |

# Implementation backlog — scale options

| Item | Status | P | Dependency | Owner |
| --- | --- | --- | --- | --- |
| Higher daily cadence | Park | 3 | True contribution + capacity | Owner |
| Selective auto-publish | Park | 3 | Stable gates + explicit approval | BalRam |
| Second niche | Park | 3 | First niche playbook | Owner |
| Second language | Park | 3 | Market case + cultural QA | Owner |
| Membership/community | Park | 3 | Return habit + service capacity | Revenue |
| Course or owned product | Park | 3 | Repeated paid problem | Owner |
| Merchandise | Remove | 3 | No current strategic fit | Owner |
| Advanced data warehouse | Park | 3 | Basic reporting limits reached | Tech |
| Large team | Remove | 3 | No proven workload/economics | Owner |
| B2B licensing | Park | 3 | Reusable IP + buyer signal | Revenue |
| Acquisition/exit readiness | Park | 3 | Stable profit + transferable operation | Owner |

# 22. Exit, pause, and pivot rules

A clear stopping rule is part of the business plan. It protects money, time, reputation, and future options.

## Pause immediately when

| Point | Meaning / action |
| --- | --- |
| 1 | A critical safety, privacy, rights, or account-security issue appears. |
| 2 | Publishing cannot confirm the approved version is live. |
| 3 | Costs or retries pass the approved automatic limit. |
| 4 | The review queue exceeds the safe deadline. |
| 5 | A platform or legal rule becomes uncertain for the planned action. |
| 6 | BalRam says “Pause all publishing now.” |

## Pivot when

| Point | Meaning / action |
| --- | --- |
| 1 | A clearly defined audience problem performs better than the current broad promise across several fair tests. |
| 2 | Evergreen content creates stronger repeat behaviour and economics than the news treadmill. |
| 3 | One platform produces higher-quality audience actions without creating dangerous dependence. |
| 4 | A revenue line shows real demand but requires a different content depth or customer segment. |
| 5 | The first niche is weak but the same operating system can test one backup niche within the remaining stop-loss. |

## Stop when

| Point | Meaning / action |
| --- | --- |
| 1 | The cumulative cash or time stop-loss is reached. |
| 2 | After a fair test, no segment shows repeat value and no credible next hypothesis remains. |
| 3 | The work repeatedly requires violating the safety, disclosure, or originality standard to perform. |
| 4 | The owner burden remains above the approved cap after simplification. |
| 5 | The expected upside no longer justifies legal, reputation, platform, or opportunity risk. |

## Orderly shutdown checklist

| Step | Action |
| --- | --- |
| 1 | Pause publishing and promotion. |
| 2 | Preserve contracts, invoices, tax, rights, and correction records. |
| 3 | Meet active sponsor and customer obligations or negotiate an exit. |
| 4 | Export audience data lawfully and honor privacy requests. |
| 5 | Cancel renewals only after assets and records are exported. |
| 6 | Archive code, media, accounts, credentials, and rebuild instructions. |
| 7 | Keep public content, redirect it, or unlist only under the lifecycle policy. |
| 8 | Document the final outcome and the conditions under which a restart would make sense. |

# 23. Sources and evidence notes

Official platform and government sources control implementation. Recheck the live page before acting because rules, thresholds, interfaces, and regional availability change.

1. YouTube channel monetization policies. https://support.google.com/youtube/answer/1311392 Supports the originality and varied-substance controls; shared format alone is not the issue.

2. YouTube altered or synthetic content disclosure. https://support.google.com/youtube/answer/14328491?hl=en&co=GENIE.Platform%3DDesktop Supports the synthetic-media disclosure record.

3. YouTube Partner Program overview. https://support.google.com/youtube/answer/72851 Observed thresholds must be rechecked for account, country, and date; meeting them does not guarantee acceptance.

4. Expanded YouTube Partner Program. https://support.google.com/youtube/answer/13429240 Supports the distinction between earlier fan-funding access and full advertising eligibility in eligible regions.

5. YouTube Data API videos.insert. https://developers.google.com/youtube/v3/docs/videos/insert Supports API-quota and unverified-project restrictions; recheck at implementation.

6. TikTok integrity and authenticity guidelines. https://www.tiktok.com/community-guidelines/en/integrity-authenticity?cgversion=2024H1update#3 Supports realistic AI-content labeling and prohibited synthetic-content controls.

7. Meta approach to labeling AI content. https://transparency.meta.com/governance/tracking-impact/labeling-ai-content Supports Meta AI labeling context.

8. Meta Instagram Reels publishing sample. https://github.com/fbsamples/reels_publishing_apis/blob/HEAD/insta_reels_publishing_api_sample/README.md Implementation reference only; live API documentation and account limits control.

9. Canada Revenue Agency: social-media influencer income. https://www.canada.ca/en/revenue-agency/news/newsroom/tax-tips/tax-tips-2021/are-you-social-media-influencer-what-to-know.html Supports business-income and non-cash-benefit recordkeeping.

10. Canada Revenue Agency: GST/HST registrants. https://www.canada.ca/en/revenue-agency/services/forms-publications/publications/rc4022/general-information-gst-hst-registrants.html Supports general small-supplier threshold discussion; exact application needs professional review.

11. Competition Bureau Canada: influencer marketing. https://competition-bureau.canada.ca/en/deceptive-marketing-practices/types-deceptive-marketing-practices/influencer-marketing-and-competition-act Supports clear, visible, post-specific material-connection disclosures.

12. U.S. Federal Trade Commission: Disclosures 101. https://www.ftc.gov/node/60343?ref=xperiencify.mymidnight.blog Supports hard-to-miss disclosure with the endorsement, including in-video disclosure.

13. Office of the Privacy Commissioner of Canada: PIPEDA breach guidance. https://publications.gc.ca/collections/collection_2021/cpvp-opc/IP54-94-2019-eng.pdf Supports breach assessment, notification, reporting, and recordkeeping planning.

14. Business Development Bank of Canada: business strategy and planning. https://www.bdc.ca/en/articles-tools/business-strategy-planning?it=business-planning/why-do-you-need-a-business-plan/& Supports deliberate planning, growth, emergency preparation, and cash discipline.

15. Google Think: short- and long-form video. https://business.google.com/us/think/search-and-video/short-and-long-form-videos/ Directional case material for using short-form discovery with deeper long-form value; it is not a forecast for this business.

## Evidence limits

| Point | Meaning / action |
| --- | --- |
| No revenue forecast | the business has no verified channel history, audience baseline, program acceptance, or sponsor pipeline. |
| No handle guarantee | public conflict searches cannot reserve a name or prove current platform availability. |
| No legal or tax opinion | the plan identifies triggers and records; qualified Canadian professionals decide account-specific treatment. |
| No platform approval guarantee | thresholds and technical eligibility do not guarantee monetization, reach, or API audit acceptance. |
| No fixed cost claim | working ranges must be replaced with selected-provider quotes, actual usage, invoices, and measured founder time. |
| No automation authorization | the plan preserves the review-first decision until explicit approval changes it. |

# 24. Plain-language glossary

| Term | Meaning |
| --- | --- |
| Adapter | A small connector that lets the core system talk to one platform or service. |
| Attribution | A reasoned link between a marketing action and a sale or other result. |
| Circuit breaker | An automatic stop that prevents repeated failures or runaway cost. |
| Contribution | Revenue left after the variable costs needed to produce that revenue. |
| Cohort | A fair comparison group measured from the same starting point. |
| Guardrail | A limit that must not be sacrificed while improving another metric. |
| Idempotency | A protection that stops a retry from creating a duplicate post or charge. |
| Knowledge base | The controlled record of evidence, tests, decisions, and failure lessons. |
| Lineage | The trail showing where a claim, file, metric, or decision came from. |
| Recovery point | The maximum recent work the business accepts losing after a failure. |
| Recovery time | The target time to restore an important service or record. |
| Residual risk | The risk still present after prevention and fallback controls. |
| Stop-loss | A pre-agreed limit on money, time, or harm that triggers a pause or stop. |
| True contribution | Contribution after counting relevant owner time, fees, refunds, and support. |
| Versioned | Saved with a clear history so an earlier approved state can be identified or restored. |

# Appendix A. Launch-readiness checklist

Launch only when every required row has an owner, evidence, and a passing result. “Planned” is not “ready.”

| Area | Required evidence |
| --- | --- |
| Strategy | Audience promise and prohibited scope approved |
| Brand | Name decision and asset-rights package complete |
| Security | Owner account, two-step security, and recovery tested |
| Editorial | Source hierarchy, claim ledger, and correction policy operating |
| Topics | Evergreen reserve and freshness rules operating |
| Media | Originality, commercial rights, privacy scan, and fallbacks tested |
| Quality | Five consecutive end-to-end items pass all gates |
| Publishing | Manual flow and independent live verification pass |
| Data | Records are versioned; missing data is visible |
| Finance | Monthly cap, stop-loss, time cap, and bookkeeping set |
| Legal/tax | Professional triggers identified; disclosure templates approved |
| Recovery | Code and media restored from independent copy |
| Incidents | Pause command and one drill pass |
| Reporting | Weekly scorecard definitions and windows locked |
| Authority | Decision rights and absence plan recorded |

## Final go / hold record

| Field | Entry |
| --- | --- |
| Decision | GO / HOLD / LIMITED PILOT |
| Scope | Platforms, pace, content lanes |
| Cash cap | Monthly and cumulative |
| Time cap | Weekly founder hours |
| Review mode | Every item / defined exception |
| Known residual risks | Accepted items from risk register |
| Decision owner | Name and date |
| Next gate | Date or evidence threshold |

# Appendix B. Monthly business review

| Question | Evidence to bring |
| --- | --- |
| Did we serve the intended audience? | Segment-level repeat behaviour, saves, questions, interviews |
| Did quality hold? | QC failures, corrections, complaints, rights/privacy events |
| Did the system deliver reliably? | Verified posts, incidents, retries, recovery results |
| Did economics improve? | Cash, owner time, contribution, payout timing, receivables |
| Did a revenue line gain proof? | Qualified clicks, conversions, partner pipeline, refunds |
| What changed outside us? | Platform policy, competitors, vendors, audience needs |
| What did we learn credibly? | Validated experiments and retired rules |
| Where is concentration dangerous? | Platform, vendor, revenue, person, topic |
| What should stop? | Low-value work, failed formats, unused tools |
| What changes next month? | Owner, dependency, measure, rollback condition |

## One-page decision record template

| Field | Question |
| --- | --- |
| Decision | What exactly is being approved, changed, parked, or stopped? |
| Reason | What evidence and business need support it? |
| Dependencies | What must be true first? |
| Cost and time | What cash, owner time, and capacity does it use? |
| Risks | What can go wrong and what remains after controls? |
| Measure | What will show success or failure? |
| Rollback | How do we return safely? |
| Owner and date | Who decides and when does it take effect? |
| Review | When or under what trigger is it reconsidered? |

# Appendix C. First 90 days — practical sequence

The schedule is evidence-led. A week may move when a dependency or quality gate is not ready; the gate does not move to protect the calendar.

| Period | Primary work | Decision / evidence |
| --- | --- | --- |
| Weeks 1–2 | Audience interviews; promise; name decision; security; editorial and rights rules | Approved scope, ownership, stop-loss, and safe accounts |
| Weeks 3–4 | Claim ledger; capture profile; media fallbacks; five private end-to-end items | Five consecutive complete QC records |
| Weeks 5–6 | Build evergreen reserve; manual platform tests; live-verification method | 14 approved topics and verified private/unlisted flow |
| Weeks 7–8 | Limited public pilot; measure owner time, cost, audience response, incidents | Continue pace, reduce pace, or repair |
| Weeks 9–10 | Test two or three recurring series and one audience call-to-action | Early audience-problem separation |
| Weeks 11–12 | Complete comparable measurement windows; restore drill; monthly close | Phase 1 evidence pack |
| Week 13 | Go / hold / pivot / stop review | Written decision and Phase 2 scope |

## Pilot sample-size discipline

| Decision | Minimum evidence before judgment |
| --- | --- |
| Kill one video | Only for a gate failure, safety issue, or clear mismatch—not low early views |
| Judge a hook/format | Several comparable posts with the same measurement window |
| Judge a series | Enough episodes to separate topic quality from one-off noise |
| Change audience promise | Multiple content tests plus direct audience evidence |
| Increase cadence | Stable QC, backlog, cost, and owner-time trend |
| Scale revenue tactic | Reconciled results, not dashboard clicks alone |

# Appendix D. Offer, pricing, and sales design

Price follows value, rights, workload, risk, and market evidence. The pilot should not publish a universal price list before those inputs are known.

| Offer | Customer result | Price inputs | Do not include by default |
| --- | --- | --- | --- |
| Affiliate recommendation | A suitable tool choice | Audience fit, program terms, support burden | Claims not independently checked |
| Sponsored Short | Qualified awareness | Reach quality, production, rights, revisions, exclusivity | Unlimited edits or perpetual paid usage |
| Sponsored long-form module | Deeper education | Research, integration, retention, rights, disclosure | Sponsor control over conclusion |
| Owned guide/template | Time saved or decision simplified | Demand evidence, maintenance, support, refunds, tax | Lifetime updates without a cost model |
| B2B license | Reusable approved content | Territory, term, media, edits, exclusivity, audience | Ownership transfer unless priced deliberately |

## Price-building worksheet

| Component | Question |
| --- | --- |
| Base production | What direct cash and human time does delivery require? |
| Risk and complexity | Are claims, revisions, approvals, or deadlines unusually demanding? |
| Usage rights | Where, for how long, and in which media may the buyer reuse it? |
| Exclusivity | What competing revenue must be refused, and for how long? |
| Distribution value | What proven audience quality and placement is included? |
| Payment risk | Is there a deposit, long term, currency cost, or default risk? |
| Margin | What surplus funds future work, incidents, tax, and owner return? |

## Sales-funnel record

| Stage | Required record | Exit condition |
| --- | --- | --- |
| Target | Company, fit reason, conflict check | Qualified or rejected |
| Contact | Consentful contact route and date | Response or close date |
| Discovery | Need, audience, timing, budget, claims | Brief accepted |
| Proposal | Scope, price, rights, dates, measures | Signed or closed-lost |
| Delivery | Approvals, proof, disclosure | Acceptance recorded |
| Payment | Invoice, due date, receipt, tax | Cash reconciled |
| Renewal | Results and fit review | Renew, change, or stop |

# Appendix E. Community, support, and reputation

| Area | Working rule | Escalate when |
| --- | --- | --- |
| Comments | Answer useful questions; hide spam; do not argue for engagement | Threat, legal claim, impersonation, coordinated abuse |
| Corrections | Thank credible corrections; investigate; show material fix | Claim affects money, safety, privacy, rights, or sponsor |
| Product support | Clarify the content; do not become unpaid vendor support | Viewer needs account-specific or professional advice |
| Testimonials | Use only with consent and context; no misleading result claims | Compensation or relationship exists |
| Impersonation | Keep an official-link page and evidence kit | Fake account solicits money or data |
| Crisis response | Pause scheduled promotion; state known facts only | Public harm is growing or counsel is needed |

## Reputation response sequence

| Step | Action |
| --- | --- |
| 1 | Capture the claim, affected content, reach, and evidence. |
| 2 | Separate factual error, opinion, harassment, platform action, and legal complaint. |
| 3 | Pause related scheduled content if continued publication could worsen harm. |
| 4 | Assign one response owner and one approved factual record. |
| 5 | Correct, disclose, remove, or decline to respond according to the evidence. |
| 6 | Review related content and controls; record what changed. |

# Appendix F. Vendor and tool selection

| Criterion | Question | Evidence |
| --- | --- | --- |
| Output quality | Does it reliably meet the content standard? | Blind sample review and failure set |
| Rights | Can outputs be used commercially and reused? | Dated terms and plan record |
| Privacy | What input/output is retained or used for training? | Contract/privacy terms |
| Reliability | What are limits, outages, and support routes? | Trial logs and status history |
| Portability | Can files, data, settings, and IDs be exported? | Test export and migration |
| Cost | What drives cost and can spending be capped? | Usage model and alerts |
| Security | How are access, audit, deletion, and incidents handled? | Security documentation and test |
| Substitute | Can another provider replace it without rewriting the core? | Working adapter or manual fallback |

# Appendix G. Quality-control certificate

Gate result: PASS The 26 September 2026 build passed the artifact checks described below. This certificate covers document construction and internal consistency; it does not convert planning assumptions into market facts or professional advice.

| Check | Method | Result |
| --- | --- | --- |
| Structure | Parsed the emitted Word file and compared its headings with the locked outline | All planned core sections present |
| Content scan | Searched extracted text for TODO, placeholder, lorem, “[insert”, and build-note language | No unresolved placeholder found |
| Quantitative labels | Reviewed money, volume, time, threshold, recovery, and phase figures | Planning figures visibly labeled as estimates, assumptions, targets, or live-rule checks |
| Source links | Inspected Word hyperlink relationships and required official URLs | Required official source links embedded |
| Render | Converted the Word file through LibreOffice and rasterized every page | All pages rendered |
| Visual review | Read every rendered page for clipping, overlap, margin collision, cramped tables, and orphaned content | No blocking layout defect found |
| Deliverable boundary | Checked project root and document metadata | One user-facing DOCX; title, creation time, and modified time present |

## Known limits of the certificate

| Limit | Meaning for use |
| --- | --- |
| External rules change | Recheck official sources before any account, disclosure, tax, or API action. |
| Business inputs are not yet observed | Replace cost and workload assumptions with invoices and measured time. |
| Professional review not performed | Use qualified Canadian tax, legal, privacy, and insurance advisers at the named triggers. |
| No live accounts inspected | The plan does not claim platform access, handle reservation, monetization eligibility, or publishing readiness. |